department of education

DIVISION OF NUEVA ECIJA

PANTABANGAN DISTRICT

CAMBITALA ELEMENTARY SCHOOL

BARANGAY CAMBITALA, PANTABANGAN NUEVA ECIJA

SCHOOL YEAR 2016-2019

Date of Submission

E N D O R S E M E N T

This is to signify our collective approval and support to the implementation of the School Improvement Plan which contains our aspirations for our school.  Signed on ______ at _________.

ANNAMARIE V.  MIRANDA

President,

General Parents-Teachers Association

MILADY G. EXALA

President

Faculty Club of CES

ANDREW C. TOLENTINO

Principal I

Cambitala Elementary School

Accepted by:

JOHANNA N. GERVACIO

Officer-in-charge

Asst. Schools Division Superintendent

ZYRILLE ANN PANTILON

President

Pupils’ Government Organization

BERNADINE ESTIGOY

Punong Barangay

Barangay Cambitala

Accepted by:

ERICSON S. SABACAN

Officer-in-charge

INTRODUCTION

The School Improvement Plan of Cambitala Elementary School (CES) of Division of Nueva Ecija was conceptualized and framed in response to and in adherence to RA 9155 also known as the Governance of Basic Education Act of 2001 which states that:

“Consistent with the national educational policies, plans and standards, the school heads shall have authority, accountability and responsibility for the following:

(1) Setting the mission, vision, goals and objectives of the school;

(2) Creating an environment within the school that is conducive to teaching and learning;

(3) Implementing the school curriculum and being accountable for higher learning outcomes;

(4) Developing the school education program and school improvement plan;

(5) Offering educational programs, projects and services which provide equitable opportunities for all learners in the community;

Good school governance entails great responsibility pursuing for greater possibilities of improvement.  The formulation of an SIP caters the total development and improvement of the school through shared responsibilities of the school and the community it serves. It is along this line that the school tapped all the stakeholders for a collaborative endeavor to attain the standards set by the School Planning Team (SPT) among and between the pupils, teachers, parents, school head and the community.

This document was realized through the collaborative efforts of the School Planning Team who include: Mr. ANDREW C. TOLENTINOP, PRINCIPAL I; Mrs. ANNAMARIE MIRANDA President of the General Parents-Teachers Association (GPTA); Mrs. MILADY G. EXALA, President of the School’s Faculty Club, ZYRILLE ANN PANTILON, President of the Pupils’ Government Organization, and, MR. BERNADINE ESTIGOY, Punong Barangay of Barangay Cambitala, Pantabangan Nueva Ecija.

This was prepared in a thorough consultation with the above-mentioned stakeholders in a 5-day seminar conducted by the National Educator’s Academy of the Philippines (NEAP). They painstakingly identified the school’s situation through SWOT analysis and other methods, identified the school’s goals and objectives, and the schools’ priorities in the next three years.

The SIP shall serve as the guide for the school head in managing the school taking into consideration the different goals and objectives in every area of the educational system. This is also a good source of information for the stakeholders, on which area, goal and objective they can extend assistance to the school head, in particular, and the school in general. The school head, using this document, may make representations and create linkages to would-be benefactors and other persons who would be extending assistance to the school in realizing the goals and objectives stated herein.

GUIDING PRINCIPLES

CAMBITALA ELEMENTARY SCHOOL believes in the following core values:

COOPERATION - observing participatory governance, all stakeholders should work for the school

EXCELLENCE - working together armed with individual proficiencies stakeholders shall strive in sustaining the increasing school performance

ACCOUNTABILITY -acting based on individual missions stakeholders have collective responsibilities towards the holistic development of the child.

VISION STATEMENT

By 2019, Cambitala Elementary School is one of the best performing eco-sustainable, child-friendly schools, with adequate facilities and services, school performances that are with the standards; quality learners who are value-oriented and do actively participate and contribute towards the building of a decent and productive society and known internationally.

MISSION STATEMENT

Through resource generation and effective curriculum implementation by accountable and competent school personnel supported by the cross-section of the school community, Cambitala Elementary School shall provide quality elementary education that is equitably accessible to all and lay foundation for life-long learning and service for common goals.

SCHOOL LOGO

The symbolic design of Cambitala Elementary School is emblazoned with several curved lines edging the logo symbolizing the existence of life and external influences that affects it. At the center of the logo is an open book (symbolizes knowledge) and a lighted torch (whose flame kept on burning which symbolizes the incessant enlightenment) back grounded by glaring rays and laurels (the highly competent learners of the school) encompasses the ideals and ambitions aspired for through the educative process; encased by a singular circle embodies the unending provision of quality basic education.

SCHOOL & COMMUNITY PROFILE

A. SCHOOL PROFILE

Cambitala Elementary School (CES) has produced a number of professionals in the past   57 years of existence as an elementary school.

CES was the DISTRICT GULAYAN SA PAARALAN WINNWER.  Lately joined SOUTH EAST ASIAN MINISTERS OF EDUCATORS ORAGANIZATION (SEAMEO) JAPAN, TRUST FOR SUSTAINABLE LIVING –SUSTAINABILITY CHALLENGE (AWARDING WILL BE HELD IN UK ON JULY 3-7, 2017)

The pupils' performance in the National Achievement Test (NAT) in Grade 3 is promising. Considering the target of 75% by 2015 set by the department, the school's performance of ______is still below the standard, yet so close to be realized.

Once adjudged as the most FUNCTIONAL HOME ECONOMICS BUILDING in 2016-2017.

The school has 260 pupils in school year 2018-2019, headed by an Elementary School Principal I which is consistent with the mandate of the School Based Management particularly the development of a globally competitive sustainable school.

There are 10 nationally funded teachers, which includes one Master Teachers, one Teachers III and eight Teachers I. Two teacher is funded by the Pantabangan Local School Board assisted by Provincial School Board.

Outside curriculum, the school wants to offer soon technology that will raise the level of community lives like electric car production technology.  Initiating also to make Pantabangan as Sister City of one of the cities in North Korea is also part of its international endeavor. Production of flour from squash, soy milk and other soy product, application for renewable energy like solar panel to bear with the global call to reduce the carbon emission and be ready when black gold meets its nearby end of supply.

Cambitala Elementary School is also the house of so called Cambitala National High School, There are 7 classrooms for the elementary and 4 classrooms for the high school. The school principal’s office, home economics building and gymnasium were part of the building structures situated in the area. The material recovery facilities, seedlings production, solar dryer, proposed “reading rain forest” was also part of the physical plan improvement. The existing Math Park, Science Park and Gulayan sa Paaralan area are in the process of improvement. Advanced technology introduced by Principal Andrew C. Tolentino like soy milk production is enjoyed by pupils in feeding program as well as school canteen.

SCHOOL HISTORY

It was said to be one of the Japanese barracks during the World War II. After the war, it has been an open area that later became children playground. Soon informal teachings among children happened that later registered the area as Cambitala Elementary School.

B. COMMUNITY PROFILE

Cambitala  is a small rural barangay on the southern part of Pantabangan, some 11 km from the municipal proper and lying at the foot of hilly feature, two kilometers from Rizal proper. It is bounded on the North by Barangay Ganduz and Sampaloc, on the South by Barangay San Juan  and on the West is Barangay  . The barangay can be reached by jeepney, tricycle and private vehicles.

The land area is 1200 hectares of agricultural land devoted to  rice, corn,  root crops, fruit trees, forest trees and vegetables. It is populated by people mostly engaged in farming.

Barangay Cambitala  has 7 political subdivisions having more or less  700 households. Its present leader is Punong Barangay Bernadine Estigoy. His administration is assisted by 7 Kagawads, 1 Treasurer and a Secretary.

The Barangay owns around 1200 sq. m. lot where the two storey Barangay Hall, Tanod Outpost, Health Center,  Day Care Centers, Barangay Multi Purpose Gymnasium which is also an  Outdoor Stage and Basketball Court.

To maintain peace and order, the Barangay Council is backed up by Barangay Tanod that guard and police the entire barangay in a shifting basis.

On the economic aspect, the barangay proper has 23 sari-sari stores offering different services such as consumer goods, school supplies, medicines, fuels, foods and other related services. Cambitala has farmer cooperatives wherein the government both DENR and DAR warded the stewardship specially to those affected by construction and establishment of Pantabangan Dam Reservoir.

On Education, Cambitala has 1 schools Educare, 1 Alternative Children’s Learning Centre called cambitala Day Care Center an Elementary School offering complete elementary and within the school ground of elementary the Cambitala National High School for four years in existence.

On Religious Aspect, Cambitala has 1 Barangay Chapel wherein a regular mass on Sundays and Holidays is celebrated. Church Leaders are active and back up by Christian Youth Organization.

Family Income and Occupation. Farmers, laborers, and animal caring are the major occupation of the head of the family earning in the range of Php 150 to Php 5,500 a month. Very few are government employees and teachers as their means of living and occupation.

Education. Majority of the residents reached Elementary level. The number and percentage obtained is actually higher of 65%. Only 18% reached school level, almost 5.26% graduated from vocational courses. Few were enrolled in Bachelor Courses.

Labor Segmentation. The labor force of the Barangay is 570. From ages 15-75, 3.89% or 13 are Professionals, 7.87 % or 26 are in Vocational and Technical field, 88.32 % or 295 focus on being a Laborer or Worker and Farmers.

SITUATION ANALYSIS

This is a presentation of the school data and accomplishments supported with the trends and factors that contributes to the underachievement of the school in different areas discussed hereunder.

PROVISION OF EQUITABLE ACCESS PERSONNEL

There are 10 nationally funded teachers, which includes one Master Teachers, one Teachers III and eight Teachers I wherein one was assigned in Cambitala Annex as well as the two teachers who were funded by Pantabangan Local School Board assisted by Provincial School Board.

All classes are mono-grade while grades 4, 5, and 6 have departmental schedules. In our Cambitala Annex multi grade system is applied.

The teacher-pupil ratio is 1:30, which is within the planning standard. The grade level ratios are all within the planning standard. Teacher-pupil ratio by grade level are: Pre-elem- 1:__; Grade 1 - 1:___; Grade 2 – 1:__; Grade 3 – 1:__; Grade 4 – 1:24; Grade 5 – 1:35 and Grade 6 – 1:34.

OUR NEEDS:

The school has no guidance counselor the school principal act as one.  The school needs additional two utility workers.

LEARNING MATERIALS & EQUIPMENT

The pupil-book ratio is within the planning standards of 1:1. All subject areas across grade levels have a ratio from 1:1 except for Grades 5 and 6 wherein k12 program is still under process including distribution of learners’ materials.

There are multi-media equipment present in the school. Sets of computer unit for the ICT Laboratory for intermediate classes can be used. At least 8 computer units are present.

Pupil-book ratio in English 1 is 1:1 which is the standard.

Pupil-book ratio in English 2 is 1:1 which is the standard.

Pupil-book ratio in English 3 is 1:1 which is the standard.

Pupil-book ratio in English 4 is 3:1 which is the standard.

Pupil-book ratio in English 5 is a special case due to reason that k12 books are still under

Process for distribution

Pupil-book ratio in English 6 is 4:1 which is below the standard of 1:1 but since it will a new curriculum of K12 next school year it is expected to have a 1:1 book ratio

Pupil-book ratio in Science 3 is 1:1 which is the standard.

Pupil-book ratio in Science 4 is 1:1 which is the standard.

Pupil-book ratio in Science 5 is a special case due to reason that k12 books are still under

Process for distribution

Pupil-book ratio in Science 6 is 4:1 which is below the standard of 1:1 but since it will a new

curriculum of K12 next school year it is expected to have a 1:1 book ratio

Pupil-book ratio in Math 1 is 1:1 which is the standard.

Pupil-book ratio in Math 2 is 1:1 which is the standard.

Pupil-book ratio in Math 3 is 1:1 which is the standard.

Pupil-book ratio in Math 4 is 1:1 which is the standard.

Pupil-book ratio in Math 5 is a special case due to reason that k12 books are still under

Process for distribution

Pupil-book ratio in Math 6 is 4:1 which is below the standard of 1:1 but since it will a new

Curriculum of K12 next school year it is expected to have a 1:1 book ratio

Pupil-books for Sibika at Kultura 1 is 1:1 which is the standard

Pupil-book ratio in Sibika at Kultura 2 is 1:1 which is the standard.

Pupil-book ratio in Sibika at Kultura 3 is 1:1 which is the standard

Pupil-book ratio in Sibika at Kultura 4 is 1:1 which is the standard.

Pupil-book ratio in Sibika at Kultura 5 a special case due to reason that k12 books are still under Process for distribution

Pupil-book ratio in Sibika at Kultura 6 is 4:1 which is below the standard of 1:1 but since it

will a new curriculum of K12 next school year it is expected to have a 1:1 book ratio

Pupil-books in MSEP 4 is 1:1 which is the standard.

Pupil-book   in MSEP 5, a special case due to reason that k12 books are still under Process for distribution

Pupil-books in MSEP 6, 4:1 which is below the standard of 1:1 but since it

will a new curriculum of K12 next school year it is expected to have a 1:1 book ratio

Pupil-book in EPP 4 is 1:1 which is the standard.

Pupil-book EPP 5 a special case due to reason that k12 books are still under Process for distribution

Pupil-books in EPP 64:1 which is below the standard of 1:1 but since it

will a new curriculum of K12 next school year it is expected to have a 1:1 book ratio

OUR NEEDS

- Acquired 1:1 book-pupil ratio in all subject areas in grade 5 and 6 levels. • 1

computer units for every class room

- Solar panel for our water system and freezer to operate.

- Solar dryer. Flour maker and bio degradable waste chopper to improve our vermin-

cast production.

PHYSICAL & ANCILLARY SERVICES

- Classroom-student ratio is 1:36 which is within the planning standard of 1:45.

- There are 11 completed classrooms in the school, but all of them are below the standard dimension of 7 x 9 meters.

- Ancillary areas such as Industrial Arts shop, Science laboratory, Library and English room is needed.

- Out of the 11 completed classrooms, 2 rooms need minor repairs for pre elem and grade 7.

- The school site is half-surrounded with concrete and permanent perimeter fence that is needed to be rehabilitated.

- Energized and supplied with electricity and water from local utility companies.

- Total pupil seats available are 260 or a 1:1 chair pupil ratio. These seats are a combination of desks, table armchairs and modular tables.

- High school department who used to use all the elementary existing chairs and tables are at present needed additional to comply with their growing grade level and student population.

- Photocopier for test reproductions is needed .

- No telephone line for outside communication.

- No internet services

OTHERS

- The school has been actively participating in a number of co-curricular activities like, but not limited to, BSP/GSP camps in various levels . These activities contribute to the holistic development of a child.

- We hosted the District Press Conference and were very active in student journalism cliniquing,

- Joining all subject areas competitions and winning in the District up to Congressional District .

- Active in National Greening Program.

- Nutrition Month celebration is well celebrated with a weeklong activity.

- DRRM activities is manifested in every classroom

OUR NEEDS

• 10 folding foam beddings, sound system, microphone and school stage rehabilitation as well as roofing from stage to multi purpose gymnasium.

QUALITY AND RELEVANCE OF BASIC EDUCATION

PUPILS’ PERFORMANCE

- The pupils' performance as to the National Achievement Test (NAT) in Grade 6 is

promising. Considering the target of 75% by 2014 set by the department, the

school's performance of 71.24 is still below the standard, yet so close to be realized.

## PUPILS’ PERFORMANCE

The pupils' performance as to the National Achievement Test (NAT) in Grade 6 is promising. Considering the target of 75% by 2015 set by the department, the school's performance of 71.24 is still below the standard, yet so close to be realized.

- Pupils' NAT performance in Filipino is 86.96, is above the planning standard, needs to be improved by 2%.

- Pupils' NAT performance in English is 75, is within the planning standard, needs to be improved by 2%.

- Pupils' NAT performance in Science is 71.18, is below the planning standard.

- Pupils' NAT performance in HEKASI is 69.90, is below the planning standard.

- Pupils' NAT performance in Mathematics is 53.14, is below the planning standard.

Hereunder is the presentation of the school’s performance in the National Achievement Tests in Grade 6 for the past five (5) years.

| NATIONAL ACHIEVEMENT TESTS RESULTS FOR GRADE SI |  |  |  |  | X |
| --- | --- | --- | --- | --- | --- |
|  | 11-12 | 12-13 | 13-14 | 14-15 | 15-16 |
| ENGLISH | 44.37 | 57.41 | 68.77 | 65.08 | 75 |
| SCIENCE | 36.10 | 37.33 | 62.43 | 67.27 | 71.18 |
| MATH | 34.27 | 45.21 | 69.1 | 64.85 | 53.14 |
| FILIPINO | 49.63 | 67.38 | 74.18 | 74.66 | 86.96 |
| SIBIKA/HEKASI | 35.87 | 53.42 | 83.36 | 76.78 | 69.9 |
| SCHOOL AVE | 40.05 | 52.15 | 71.57 | 69.73 | 71.24 |

Set by the department in school year 2017-2018 with 81.09 MPS. This put the school in the great spot among schools in the District of Pantabangan.

All subject areas tested in the NAT 3 are above the standard, but Filipino (Reading).

Hereunder is a summary table and a graph of the results:

| NATIONAL ACHIEVEMENT TESTS RESULTS IN GRADE THREE |  |  |  |
| --- | --- | --- | --- |
|  | 2015-2016 | 2016-2017 | 2017-2018 |
| ENGLISH (READING) | 66.62 | 47.48 | 81.58 |
| FILIPINO (READING) | 67.72 | 45.07 | 71.86 |
| ENGLISH (GRAMMAR) | 80.13 | 57.91 | 83.37 |
| FILIPINO (GRAMMAR) | 55.82 | 51.19 | 87.37 |
| SCIENCE | 79.75 | 49.95 | 81.97 |
| MATH | 71.98 | 42.99 | 83.39 |
| SCHOOL AVE | 70.23 | 48.18 | 81.09 |

The 2017-2018 Division Achievement Test results is 69.54, which is below the planning standard.

- Pupils' DAT performance in Science is 87.07, is above the planning standard.

- Pupils' DAT performance in EPP is 75.94, is above the planning standard.

- Pupils' DAT performance in Filipino is 75.33, is above the planning standard.

- Pupils' DAT performance in HEKASI is 70.34, is below the planning standard.

- Pupils' DAT performance in MSEP is 66.26, is below the planning standard.

- Pupils' DAT performance in English is 65.32, is below the planning standard.

- Pupils' DAT performance in Mathematics is 58.20, is below the planning standard.

| DIVISION ACHIEVEMENT TESTS RESULT FOR THE PAST FIVE (5) YEARS |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | 2013-2014 | 2014-2015 | 2015-2016 | 2016-2017 | 2017-2018 |
| ENGLISH | 49.50 | 55.90 | 61.28 | 57.80 | 65.32 |
| MATH | 44.04 | 48.38 | 47.57 | 73.85 | 58.20 |
| SCIENCE | 47.50 | 37.99 | 47.69 | 66.51 | 87.07 |
| FILIPINO | 65.44 | 62.45 | 69.70 | 68.17 | 75.33 |
| HEKASI | 47.72 | 64.02 | 65.45 | 68.65 | 58.65 |
| EPP | 43.76 | 66.07 | 75.62 | 71.91 | 75.94 |
| MSEP | 52.16 | 59.82 | 59.83 | 82.04 | 66.26 |
| SCHOOL AVE | 51.00 | 56.38 | 61.02 | 69.85 | 69.54 |

|  | ENGLISH |  |  |
| --- | --- | --- | --- |
| LEVEL | 2015-2016 | 2014-2014 | 2017-2018 |
| I | 71.31 | 48.84 | 68.77 |
| II | 53.99 | 56.65 | 43.47 |
| III | 57.87 | 68.63 | 85.78 |
| IV | 76.07 | 65.95 | 70.95 |
| V | 47.52 | 57.87 | 57.68 |
| VI | 60.90 | 48.88 | 65.24 |

|  | MATH |  |  |
| --- | --- | --- | --- |
| LEVEL | 2015-2016 | 2016-2017 | 2017-2018 |
| I | 58.17 | 66.76 | 54.57 |
| II | 36.57 | 59.46 | 38.07 |
| III | 35.50 | 87.65 | 72.46 |
| IV | 58.40 | 89.93 | 61.49 |
| V | 45.12 | 65.79 | 49.42 |
| VI | 51.65 | 73.48 | 73.17 |

|  | MSEP |  |  |
| --- | --- | --- | --- |
| LEVEL | 2015-2016 | 2016-2017 | 2017-2018 |
| IV | 52.94 | 67.96 | 58.36 |
| V | 55.52 | 93.01 | 63.95 |
| VI | 71.02 | 85.16 | 76.47 |

|  | SCIENCE |  |  |
| --- | --- | --- | --- |
| LEVEL | 2015-2016 | 2016-2017 | 2017-2018 |
| I | 58.17 | 66.76 | 54.57 |
| II | 36.57 | 59.46 | 38.07 |
| III | 35.50 | 87.65 | 72.46 |
| IV | 58.40 | 89.93 | 61.49 |
| V | 45.12 | 65.79 | 49.42 |
| VI | 51.65 | 73.48 | 73.17 |

|  | HEKASI |  |  |
| --- | --- | --- | --- |
| LEVEL | 2015-2016 | 2016-2017 | 2017-2018 |
| I | 82.15 | 64.03 | 70.15 |
| II | 60.12 | 56.48 | 42.51 |
| III | 58.03 | 67.5 | 89.76 |
| IV | 62.95 | 70.8 | 74.46 |
| V | 56.09 | 72.65 | 68.58 |
| VI | 73.40 | 80.45 | 76.59 |

|  |  | EPP |  |
| --- | --- | --- | --- |
| LEVEL | 2015-2016 | 2016-2017 | 2017-2018 |
| IV | 76.62 | 70.68 | 77.22 |
| V | 66.69 | 78.64 | 70.18 |

| Reading Level | 2015-2016 |  | 2016-2017 |  | 2017-2018 |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | n | % | n | % | n | % |
| Frustration | 26 0 | 54.74 | 29 2 | 71.39 | 23 7 | 48.57 |
| Instructional | 13 3 | 28.00 | 86 | 21.03 | 14 6 | 29.91 |
| Independent | 82 | 17.26 | 31 | 7.58 | 10 5 | 21.52 |
| Totals | 47 5 |  | 40 9 |  | 48 8 |  |

The pupils’ reading abilities are fluctuating as indicted in the three-year results of the Philippine Informal Reading Inventory (Phil-IRI). The increasing number pupils with reading levels of independent and instructional shows improvement in school year 2017-2018, thus, giving inverse impact to the frustration level.

Curriculum Implementation & Instructional Delivery

The school has observed 206 school days set by the Department last school year. Several programs and projects are being implemented to augment pupils’ learning and improve the pupils’ performances.

The school is continuously moving on in the implementation of the Eco Sustainable and Child Friendly School System (CFSS). Luckily the school was included in the list of schools in the District of Pantabangan and Division of Nueva Ecija to be evaluated in school year 2018-2019 as part of the areas appraised in National Search for Sustainable and Eco Friendly School.

The Municipal Government of Pantabangan is aware of the last year’s search where Principal Andrew C. Tolentino’s school won first in the regional level and become finalist in the national level.

Also, joined the Trust for Sustainable Living Sustainability (TSL) Challenge an International competition on sustainability wherein Principal Andrew C. Tolentino’s  former Sampaloc Elementary School won and was  chosen as 2016 International Sustainability Challenge awardee..

CES is headed by a Principal I supported by 10 nationally-funded teachers, two are funded by the Local School Board of Pantabangan through the SEF.

Among the 1 teachers, one is 50 years old, 3 are 40-45 years old, three of them are 30 – 39 years, 3 of them are 25 – 29 years old.

Among the 10, only one is a master’s degree holder while four has masters units.

Staff Development

The teachers as the main factor in the realization of the school vision were given the chance to attend seminars and training to enhance competencies and improve their effectiveness and efficiency in their tasks as teachers. Master teacher is advice to focus in making a plan for review of the crème of the crop in all subject areas in preparation for next future competition.

Teachers were also encouraged by the school principal to enroll in their graduate study and to uplift their economic status through promotions.

Staff Development

The teachers as the main factor in the realization of the school vision were given the chance to attend seminars and training to enhance competencies and improve their effectiveness and efficiency in their tasks as teachers. Teachers were also encouraged by the school head to uplift their economic status through promotions.

Nine out of ten teachers are computer literates which are higher than the planning standard.

All 10 teachers have undergone the orientation on the NCBTS-TSNA (National Competency- Based Teacher Standards - Teachers Strengths and Trainings Needs Assessment) . Also all 10 teachers are preparing their Individual Personal and Professional Development plans based on the results of the NCBTS-TSNA. Corollary to this, all teachers have attended in-service trainings (INSETs) introduced by the national, regional and division offices, though without closely considering their respective IPPDs and the results of the NCBTSTSNA.

School Improvement Plan

Cambitala Elementary School

School Year 2016-2019

TEACHER’S PROFILE

| Name of Teachers | Sex | Civil Status | Date of Birth | Position Title | Date of Original Appt. | Eligibility | Highest Educational Attainment | Area of Specialization |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. Princess G. Gonzales | F | S |  | T-I |  |  |  |  |
| 2. Jeramie Gray Boado | F | S |  | T-I |  |  |  |  |
| 3. Milady G. Exala | F | M |  | MT-I |  |  |  |  |
| 4. Dolores M. Baltazar | F | M |  | T-III |  |  |  |  |
| 5.Geraldine Piedad | F | M |  | T-I |  |  |  |  |
| 6. Shirley Pacol | F | M |  | T-I |  |  |  |  |
| 7. Sharry Ann S. Ganareal | F | M | 12-7-74 | T-I | 7-15-15 | PBET-LET | MAED THESIS WRITING | ENGLISH AND HOME ECONOMICS |
| 8. Jessica A. Nuesca | F | M |  | T-I |  |  |  |  |
| NON TEACHING PERSONNEL |  |  |  |  |  |  |  |  |
| 1. Andrew C. Tolentino | M | M | 11-30-61 | PRINCIPAL I |  | PBET | MA PSYCO | Admin and Supervision AGRICULTURAL EDUCATION MAJOR IN AGRI-ENG. |

Six teachers are attending graduate studies, our Master Teacher finished units required while our school principal is a graduate of Master or Arts in Psychology.

Group picture

## Health Status of Students/Pupils

The health status of the pupils is one of the key concerns of the school to make the teaching-learning experience be effective. In the past years, a number of programs were implemented to ensure that pupils are in good health while learning in school. These programs include:

- Deworming - This was given twice a year for Grade I pupils conducted by the medical team of the Division, which started one month after the opening of classes.

- Dental Check-up and extraction - The program’s emphasis is to maintain healthy and cavity-free teeth by giving tips on oral health and correct tooth brushing.

- Supplementary Feeding  - The school was one of the recipients of the “Soy Milk”

Milk Feeding program of the school canteen as instructed by the principal in coordination with the SUPPLEMETAL FEEDING PROGRAM of the Department of Education Division of Nueva Ecija. The feeding was given to 36 pupils who were found out to have a nutritional status of below normal.

School Improvement Plan

Cambitala Elementary School

School Year 2016-2019

Pupil Services

Programs in school on the different monthly celebrations are conducted on a regular basis to make the pupils aware and familiarized about it.

Basically, the SUPREME PUPIL’S GOVERNMENT (SPG) has been helpful in the pupils’ development and training of their leadership potentials. A number of interest clubs were organized for the pupils’ diverse interests, which includes the Junior/Kiddie Fire Marshall, MATH CLUB, ENGLISH CLUB, YES-O AND SCIENCE CLUB and other clubs related to different academic areas. A group of pupils were organized to form the editorial board of the school’s publication, PANDAWANGAN GENRE was the name of school paper.

Teams in different sports events were also organized such as, but not limited to, volleyball, sepak takraw, athletics, badminton, chess, table tennis, and others, and contested/participated in the district and division level contests. As a result, sportsmanship, camaraderie and competitiveness were developed among pupils.

Meanwhile, the Boy and Girl Scouting movement has been actively participating in a number of encampments from district, division and regional levels, held in the past years. Most of the pupils are registered members to the BSP and GSP through their parents’ membership in the city government of Naga’s QUEEN program. Learning Environment

Being located at the foot of hilly the school’s ambiance is generally conducive to learning despite some deficiency in facilities and equipment.

All classes were mono-grade and observe departmental schedules. All classes have less than 45 pupils per class, which is above the standard set by the department.

There are no cases of pupil-pupil conflict. This may be attributed to the school head’s fatherly figure felt by the school community.

There are zero recorded theft and robbery incidents against school properties for the past years

School Management School Management & Administration

The achievements earned by Cambitala Elementary School may be attributed to the school personnel’s attitude towards work. There is dynamism in each of the teaching and nonteaching personnel as well as the parents and utility workers both from Department of education MOOE funding and Local Government –Mayor’s Office assigned and the community as a whole.

All personnel come on time and are rarely late in reporting to school, or are going home early. No personnel are absent at least 5 times a month.  All personnel attend school activities and submit reports regularly on time.

Alumni/Parents’ Participation

Parents’ support is very much important to every pupil’s learning. Teachers are the second parents; parents are the original teachers to children. Their participation to school activities encourages the pupils to continue their quest for education.

Parents participation were noted to only 80% parents out of 260 participate in the Brigada Eskwela; only  200 parents our of  260attended two General PTA Assemblies; and, only 220 parents out of 260 parents attended Homeroom PTA meetings.

As of today there is a need to have one organized and active alumni association in the school.

Instructional Supervision

Supervisors assist the school head in developing teachers’ potentials and improve their respective talents and ability. Education Program Supervisors (EPS) Rowena Castillo together with SGOD Chief Dr. Luis Calison once visited the school this school year for a Dispute Resolution between Elementary Teachers query and School Head of Cambitala National High School existing in the ground of Cambitala Elementary School for four years now.

The Public School District Supervisor Dr. Amelia P. Nebres contributed around 20 visits since the emersion period of Principal Andrew C. Tolentino during the Brigada Eskwela time.

On the other hand, the school principal made 10 instructional supervisions every month for every teacher in each grade level.

There is a need to maximize the efforts of the above named supervisors to take full advantage of their expertise to make CAMBITALA ELEMENTARY SCHOOL AN INTEGRATED SCIENCE BASED HIGH SCHOOL while before Cambitala National High School and elementary they are existing in one area and must be under the supervision of one principal and a school head for the high school department but jointly sharing in the improvement of physical and instructional aspect of the school they belong.

With these, the continuous hearing was advised and chaired by PSDS Dr. Nebres but never was a time that may Guillermo the High School Principal attended the meeting called by the supervisor.

The high school could hardly procure what it needs to improve its performance and services. That is because the school MOOE is managed by the high school school head which maybe have different focus of improvement. The Municipality of Pantabangan Local School Board has allocated funds from the Special Education Fund for the allowance of some utility workers. There is an allocation directly for the school from the barangay budget approved by Sangguniang Barangay headed by Barangay Captain Bernadine Estigoy amounting to two hundred thousand more or less for the roofing of pathways.

As of now, for 2017 budget, Sangguniang Barangay of Cambitala is planning to allocate fund for another project intended for Cambitala Elementary School.

Performance Indicators

Graduation Rate is 100% which is within the planning standard,

Participation Rate is 95.91% which is below the planning standards of 100%.

Drop-Out Rate is 2.74%, which is below the planning standard.

Repetition Rate is 8.17% which is below the planning standard.

Failure Rate is 8%, which is below the planning standard.

SCHOOL GOALS & OBJECTIVES

The school’s goals and objectives for the next three years are stated in the table hereunder:

## Resource Mobilization/Public Expenditure/School Financial, Fiscal

## Management

The school could procure what it needs to improve its performance and services.

That is because the school MOOE is managed on the school based. The Municipality of Pantabangan Local School Board has assigned utility workers from the Special Education Fund. There is also an allocation directly for the school in the barangay budget which funded the construction of roofing of pathways.

# Performance Indicators

Graduation Rate is 100% which is within the planning standard

Participation Rate is 95.91% which is below the planning standards of 100% Drop-Out Rate is 2.74%, which is below the planning standard. Repetition Rate is 8.17% which is below the planning standard.

Failure Rate is 8%, which is below the planning standard.

SCHOOL GOALS & OBJECTIVES

The school’s goals and objectives for the next three years are stated in the table hereunder:

| Narrative Summary | Objectively Verifiable Indicators |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Means of Verification | Important Assumptions/ Risks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Goal |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Improved school performance in the District of Pantabangan, Division of Nueva Ecija |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Purpose | BY 2019 overall pupils/students achievement increased from 71.24% to 77% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | NAT Result | NETRC prepares & administers test |
| Improved student and school performance of Cambitala Elementary School |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Baseline | Yr 1 |  |  |  | Yr 2 |  |  |  |  | Y3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 71.24% | 73% |  |  |  | 75% |  |  |  |  | 77% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | By 2019 pupils/students achievement increased in the following subjects: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Subjects |  | Baseline |  |  |  |  |  | Yr1 |  |  |  |  |  | Yr2 |  |  |  |  |  |  | Yr3 |  |  |  |
|  | Science |  | 71.18% |  |  |  |  |  | 73% |  |  |  |  |  | 75% |  |  |  |  |  |  | 77% |  |  |  |
|  | English |  | 75% |  |  |  |  |  | 76% |  |  |  |  |  | 77% |  |  |  |  |  |  | 78% |  |  |  |
|  | Mathematics |  | 53.14% |  |  |  |  |  | 58% |  |  |  |  |  | 63% |  |  |  |  |  |  | 75.10% |  |  |  |
|  | Filipino |  | 86.96% |  |  |  |  |  | 88% |  |  |  |  |  | 89% |  |  |  |  |  |  | 90 % |  |  |  |
|  | Araling |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Panlipunan |  | 69.90% |  |  |  |  |  | 72% |  |  |  |  |  | 74% |  |  |  |  |  |  | 77 % |  |  |  |
| CONTRIBUTORY OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| A. Provision of Equitable Access |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| a.1. hired competent and adequate teaching & non-teaching personnel | a.1.1. Two (2) teaching personnel hired |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Personnel |  |  |  |  | Yr 1 |  |  |  |  | Yr 2 |  |  |  |  |  |  | Yr 3 |  |  |  |  |  | Approved Appointment Papers | DBM releases item for: |
|  | Guidance Counselor |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  |  |  | 0 |  |  |  |  |  |  |  |
|  | Librarian |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  |  |  | 0 |  |  |  |  |  |  |  |
|  | Teacher in Tuli |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  |  |  | 1 |  |  |  |  |  |  | Teacher |
|  | Pre-school Teacher in Tuli |  |  |  |  | 1 |  |  |  |  | 0 |  |  |  |  |  |  | 1 |  |  |  |  |  |  | Pre-School Teacher |
| a.2. Improved availability of Instructional and learning materials | a.2.1. Procured the following materials: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Delivery Receipt Inspection Report Delivery Receipt Inspection Report | IMCS delivers books |
|  | Equipment |  |  | Yr 1 |  |  |  |  |  | Yr 2 |  |  |  |  |  | Yr 3 |  |  |  |  |  | Total |  |  |  |
|  | Computers |  |  |  |  |  |  |  |  | 3 |  |  |  |  |  | 4 |  |  |  |  |  | 7 units |  |  |  |
|  | Industrial Arts |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Hammer |  |  | 1 |  |  |  |  |  | 1 |  |  |  |  |  | 1 |  |  |  |  |  | 3 |  |  |  |
|  | Saw |  |  | 1 |  |  |  |  |  | 1 |  |  |  |  |  | 1 |  |  |  |  |  | 3 |  |  |  |
|  | Tape measure |  |  | 1 |  |  |  |  |  | 1 |  |  |  |  |  | 1 |  |  |  |  |  | 3 |  |  |  |
|  | Home Economics |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Sewing machine |  |  | 3 |  |  |  |  |  | 0 |  |  |  |  |  | 0 |  |  |  |  |  | 3 |  |  |  |
|  | Oven |  |  | 1 |  |  |  |  |  | 0 |  |  |  |  |  | 0 |  |  |  |  |  | 1 |  |  |  |
|  | LPG tank |  |  | 1 |  |  |  |  |  | 0 |  |  |  |  |  | 0 |  |  |  |  |  | 1 |  |  |  |
|  | Agriculture/Gardening tools |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Rake |  |  | 4 |  |  |  |  |  | 0 |  |  |  |  |  | 0 |  |  |  |  |  | 4 |  |  |  |
|  | Spade |  |  | 2 |  |  |  |  |  | 0 |  |  |  |  |  | 1 |  |  |  |  |  | 3 |  |  |  |
|  | Hoe |  |  | 4 |  |  |  |  |  | 0 |  |  |  |  |  | 0 |  |  |  |  |  | 4 |  |  |  |
|  | Sprinkler |  |  | 5 |  |  |  |  |  | 0 |  |  |  |  |  | 0 |  |  |  |  |  | 5 |  |  |  |
|  | Bolo |  |  | 5 |  |  |  |  |  | 0 |  |  |  |  |  | 0 |  |  |  |  |  | 5 |  |  |  |
|  | Others |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Tents |  |  | 4 |  |  |  |  |  | 0 |  |  |  |  |  | 0 |  |  |  |  |  | 4 |  |  |  |
|  | Water Dispenser |  |  | 2 |  |  |  |  |  | 0 |  |  |  |  |  | 2 |  |  |  |  |  | 4 |  |  |  |
|  | Solar Panel |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | a.2.2. Procured/accepted the following textbooks |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | to achieve 1:1 textbook pupil/student ratio |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Textbooks | Yr 0 |  |  |  | Yr 1 |  |  |  |  | Yr 2 |  |  |  |  |  |  | Yr 3 |  |  |  |  |  |  |  |
|  | English |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Grade 1 | 45 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  |  |  | 0 |  |  |  |  |  |  |  |
|  | Grade 2 | 45 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  |  |  | 0 |  |  |  |  |  |  |  |
|  | Grade 3 | 45 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  |  |  | 0 |  |  |  |  |  |  |  |
|  | Grade 4 | 45 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  |  |  | 0 |  |  |  |  |  |  |  |
|  | Grade 5 | 0 |  |  |  | 45 |  |  |  |  | 0 |  |  |  |  |  |  | 0 |  |  |  |  |  |  |  |
|  | Grade 6 | 0 |  |  |  | 0 |  |  |  |  | 45 |  |  |  |  |  |  | 0 |  |  |  |  |  |  |  |
|  | Science |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Grade 3 | 45 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  |  |  | 0 |  |  |  |  |  |  |  |
|  | Grade 4 | 45 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  |  |  | 0 |  |  |  |  |  |  |  |
|  | Grade 5 | 0 |  |  |  | 45 |  |  |  |  | 0 |  |  |  |  |  |  | 0 |  |  |  |  |  |  |  |
|  | Grade 6 | 0 |  |  |  | 0 |  |  |  |  | 45 |  |  |  |  |  |  | 0 |  |  |  |  |  |  |  |
|  | Filipino |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Grade 1 | 45 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  |  |  | 0 |  |  |  |  |  |  |  |
|  | Grade 2 | 45 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  |  |  | 0 |  |  |  |  |  |  |  |
|  | Grade 3 | 45 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  |  |  | 0 |  |  |  |  |  |  |  |
|  | Grade 4 | 45 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  |  |  | 0 |  |  |  |  |  |  |  |
|  | Grade 5 | 0 |  |  |  | 45 |  |  |  |  | 0 |  |  |  |  |  |  | 0 |  |  |  |  |  |  |  |
|  | Grade 6 | 0 |  |  |  | 0 |  |  |  |  | 45 |  |  |  |  |  |  | 0 |  |  |  |  |  |  |  |
|  | Math |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Grade 1 | 45 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  |  |  | 0 |  |  |  |  |  |  |  |
|  | Grade 2 | 45 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  |  |  | 0 |  |  |  |  |  |  |  |
|  | Grade 3 | 45 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  |  |  | 0 |  |  |  |  |  |  |  |
|  | Grade 4 | 45 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  |  |  | 0 |  |  |  |  |  |  |  |
|  | Grade 5 | 0 |  |  |  | 45 |  |  |  |  | 0 |  |  |  |  |  |  | 0 |  |  |  |  |  |  |  |
|  | Grade 6 | 0 |  |  |  | 0 |  |  |  |  | 45 |  |  |  |  |  |  | 0 |  |  |  |  |  |  |  |
|  | Sibika/HKS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Grade 1 | 45 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  |  |  | 0 |  |  |  |  |  |  |  |
|  | Grade 2 | 45 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  |  |  | 0 |  |  |  |  |  |  |  |
|  | Grade 3 | 45 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  |  |  | 0 |  |  |  |  |  |  |  |
|  | Grade 4 | 45 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  |  |  | 0 |  |  |  |  |  |  |  |
|  | Grade 5 | 0 |  |  |  | 45 |  |  |  |  | 0 |  |  |  |  |  |  | 0 |  |  |  |  |  |  |  |
|  | Grade 6 | 0 |  |  |  | 0 |  |  |  |  | 45 |  |  |  |  |  |  | 0 |  |  |  |  |  |  |  |
|  | EPP |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Grade 4 | 45 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  |  |  | 0 |  |  |  |  |  |  |  |
|  | Grade 5 | 0 |  |  |  | 45 |  |  |  |  | 0 |  |  |  |  |  |  | 0 |  |  |  |  |  |  |  |
|  | Grade 6 | 0 |  |  |  | 0 |  |  |  |  | 45 |  |  |  |  |  |  | 0 |  |  |  |  |  |  |  |
|  | MSEP |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Grade 4 | 45 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  |  |  | 0 |  |  |  |  |  |  |  |
|  | Grade 5 | 0 |  |  |  | 45 |  |  |  |  | 0 |  |  |  |  |  |  | 0 |  |  |  |  |  |  |  |
|  | Grade 6 | 0 |  |  |  | 0 |  |  |  |  | 45 |  |  |  |  |  |  | 0 |  |  |  |  |  |  |  |
| a.3. Improved Physical environment for learning | a.3.1. Constructed, Accepted & Turned over the following facilities |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Actual facilities Certificate of Acceptance | DepED Central Office allocates funds for the purpose Barangay LGU Municipal International Grant Personal donation |
|  | Facility | Yr 1 |  |  |  |  |  | Yr 2 |  |  |  |  | Yr 3 |  |  |  |  |  |  | Total |  |  |  |  |  |
|  | IA shop | 0 |  |  |  |  |  | 1 |  |  |  |  | 0 |  |  |  |  |  |  | 1 |  |  |  |  |  |
|  | H.E | 1 |  |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  |  |  | 1 |  |  |  |  |  |
|  | School |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Nursery | 1 |  |  |  |  |  | 1 |  |  |  |  | 1 |  |  |  |  |  |  | 3 |  |  |  |  |  |
|  | Science lab | 0 |  |  |  |  |  | 0 |  |  |  |  | 1 |  |  |  |  |  |  | 1 |  |  |  |  |  |
|  | Computer |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | lab | 1 |  |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  |  |  | 1 |  |  |  |  |  |
|  | Perimeter fence | 60 m span |  |  |  |  |  | 50 m span |  |  |  |  | 4 0 m span |  |  |  |  |  |  | 150 m span |  |  |  |  |  |
|  | a.3.2. Repaired, accepted & turned over the |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Actual facilities Certificate of Acceptance | DepED Central Office allocates funds for the purpose Congressional Fund |
|  | following facilities: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Facility | Yr 1 |  |  |  | Yr 2 |  |  |  |  | Yr 3 |  |  |  |  |  |  | Total |  |  |  |  |  |  |  |
|  | Classroom | 6 |  |  |  | 4 |  |  |  |  | 2 |  |  |  |  |  |  | 12 |  |  |  |  |  |  |  |
|  | Library | 0 |  |  |  | 0 |  |  |  |  | 1 |  |  |  |  |  |  | 1 |  |  |  |  |  |  |  |
|  | Computer |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Lab. | 0 |  |  |  | 0 |  |  |  |  | 1 |  |  |  |  |  |  | 1 |  |  |  |  |  |  |  |
|  | a.3.3. School perimeter fence completed |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Actual facilities Certificate of Acceptance | LGU Pantabangan |
|  | Yr 0 | Yr 1 |  |  |  | Yr 2 |  |  |  |  | Yr 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 70% | 80% |  |  |  | 90% |  |  |  |  | 100% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| B. Quality and Relevance of Basic Education |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| b.1. Improved READING skills in English subjects | b.1.1. All students read within their standard reading level (independent readers) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Post Phil-IRI Report |  |
|  | Yr 0 | Yr 1 |  |  |  | Yr 2 |  |  |  |  | Yr 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 185 | 200 |  |  |  | 215 |  |  |  |  | 230 |  |  |  |  |  |  | 245 |  |  |  |  |  | 260 |  |
| b.2. Improved skills of pupils in Science, Mathematics, HEKASI | b.2.1. Organized review classes in all subjects and grade levels starting November 2016 to February 2017 and the years thereafter |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Monitoring Report Class Record |  |
| b.3. Improved Curriculum Implementation and Instructional Delivery | b.3.1. 100% of school days met or delivered per year |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | FORM 2 |  |
|  | b.3.2. 100% of pupils are promoted considering the "no read, no move" principle of the Every Child a Reader Program (ECARP) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Phil-IRI Results |  |
|  | b.3.3. 100% of the Grade I entrants have ECD |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | experiences |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Form 3 |  |
|  | b.3.4. 100% of the Grade I Entrants have been positively considered under School Readiness |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | SReA Result |  |
|  | Assessment |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| b.4. Improved subject knowledge/ teaching skills of teachers | b.4.1. Number of teachers trained on results of NCBTS/TSNA |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Attendance Sheet Training Completion Report |  |
|  | Baseline | Yr 1 |  |  |  | Yr 2 |  |  |  |  | Yr 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 10 | 10 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | b.4.2. Teachers trained on Computer Literacy: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Attendance Sheet & Training Completion Report |  |
|  |  |  |  |  |  | Yr 1 |  |  |  |  | Yr 2 |  |  |  |  |  |  | Yr 3 |  |  |  |  |  |  |  |
|  | Computer Literacy |  |  |  |  | 5 |  |  |  |  | 3 |  |  |  |  |  |  | 2 |  |  |  |  |  |  |  |
|  | b.4.3. 10 out of 10 teachers subscribed to professional magazines |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Subscription to professional magazines |  |
|  | b.4.4. 10 out of 10 teachers are master’s degree holder or earned necessary units to be promoted |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Diploma or special order |  |
|  | b.4.5. 5 out of 10 teachers and School Principal conducted one action research each a year |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Copy of approved research proposal and recommendation |  |
| b.5. Improved Nutritional status of pupils/students | b.5.1. 80% of students within normal status of nutrition |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Report of Nutritional Status |  |
|  | Yr 0 | Yr 1 |  |  |  | Yr 2 |  |  |  |  | Yr 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 200 | 220 |  |  |  | 240 |  |  |  |  | 260 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | b.5.2. Fee ding Program implemented in 6 sustained months |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Monitoring Report |  |
| C. School Management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| c.1. Instructional Supervision Strengthened | c.1.1. Frequency of supervision |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Supervisory Report |  |
|  | Supervisors | Yr 1 |  |  |  |  |  | Yr 2 |  |  |  |  |  |  |  |  | Yr 3 |  |  |  |  |  |  |  |  |
|  | School Head | 10 out of 10 / month |  |  |  |  |  | 10 out of 10 / month |  |  |  |  |  |  |  |  | 10 out of 10 / month |  |  |  |  |  |  |  |  |
|  | PSDS | 10 out of 10 / quarter |  |  |  |  |  | 10 out of 10 / quarter |  |  |  |  |  |  |  |  | 10 out of 10 / quarter |  |  |  |  |  |  |  |  |
|  | ES | 10out of 10 / sem |  |  |  |  |  | 10 out of 10 / sem |  |  |  |  |  |  |  |  | 10 out of 10 / sem |  |  |  |  |  |  |  |  |
|  | c.1.2. Number of teacher supervised |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Supervisory Report |  |
|  | Supervisors | Yr 1 |  |  |  |  |  | Yr 2 |  |  |  |  |  |  |  |  | Yr 3 |  |  |  |  |  |  |  |  |
|  | School Head | 10out of 10 / month |  |  |  |  |  | 10 out of 10 / month |  |  |  |  |  |  |  |  | 10 out of 10 / month |  |  |  |  |  |  |  |  |
|  | PSDS | 10 out of 10 /quarter |  |  |  |  |  | 10 out of 10 / quarter |  |  |  |  |  |  |  |  | 10 out of 10 / quarter |  |  |  |  |  |  |  |  |
|  | ES | 10 of 10 / sem |  |  |  |  |  | 10 of 10 / sem |  |  |  |  |  |  |  |  | 10 of 10 / sem |  |  |  |  |  |  |  |  |
| c.2. Effective School Management and Administration Implemented | c.2.1. 100% of teachers report to school on time. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Daily time Record |  |
|  | c.2.2. 100% of teachers have no more than 1 day absence in a month. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Daily time Record |  |
|  | c.2.3. 100% of the number of contact time observed by 2019 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Monitoring Report |  |
|  | c.2.4. 10 out of 10 teachers making home visits |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Monitoring Report |  |
|  | Yr 0 | Yr 1 |  |  | Yr 2 |  |  |  |  |  | Yr 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 0 | 7 |  |  | 9 |  |  |  |  |  | 10 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | c.2.5. PTA board conducts 10 meetings in a school year |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Attendance Record & Record of minutes |  |
|  | c.2.6. One Supreme Pupil Government organized and made functional |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Existence of SPG |  |
|  | c.2.7. Fifteen school INSET prepared and implemented. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Training Completion Report |  |
|  |  | Yr 1 |  |  | Yr 2 |  |  |  |  |  | Yr 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | 15 |  |  | 15 |  |  |  |  |  | 15 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| c.3. Stakeholders Participation Intensified | c.3.1. Parents attendance to PTA activities. Number of parents attended PTA meeting |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Attendance Sheet |  |
|  | Meeting |  |  |  | Yr 1 |  |  |  |  |  |  | Y r 2 |  |  |  |  |  |  | Yr 3 |  |  |  |  |  |  |
|  | Brigada Eskwela |  |  |  | 180 |  |  |  |  |  |  | 200 |  |  |  |  |  |  | 260 |  |  |  |  |  |  |
|  | General PTCA |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Assembly |  |  |  | 180 |  |  |  |  |  |  | 200 |  |  |  |  |  |  | 260 |  |  |  |  |  |  |
|  | Homeroom PTCA |  |  |  | 180 |  |  |  |  |  |  | 200 |  |  |  |  |  |  | 260 |  |  |  |  |  |  |
|  | c.3.2. One (1) Alumni Association organized and made functional by 2018 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | By – Laws Database is present |  |
|  | c.3.3. Increased financial investment by LGU’s. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Financial Report |  |
|  | Amount invested by LGU’s |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | LGU | Yr 0 |  |  | Yr 1 |  |  |  |  |  |  | Y r 2 |  |  |  |  |  |  | Yr 3 |  |  |  |  |  |  |
|  | Brgy | 0 |  |  | 1% of Bgy. EdCom |  |  |  |  |  |  | 1 % of Bgy. EdCom |  |  |  |  |  |  | 1% of Bgy. EdCom |  |  |  |  |  |  |
|  | SB Educ | 0 |  |  | 1% of Ed. fund |  |  |  |  |  |  | 1% of Ed. fund |  |  |  |  |  |  | 1% of Ed fund |  |  |  |  |  |  |
|  | SEF | 20 |  |  | 40 T |  |  |  |  |  |  | 80T |  |  |  |  |  |  | 100 T |  |  |  |  |  |  |
|  | c.3.4. Increased financial investment by PTCA. Amount invested by PTCA |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Financial Report |  |
|  | PTCA | Yr 1 |  |  | Yr 2 |  |  |  |  |  | Yr 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | GPTCA | P 50.00@ |  |  | P 50.00@ |  |  |  |  |  | P 50.00@ |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | c.3.5. 100% of pupils are covered by the insurance policy program |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Database is present Monitoring Report |  |
|  | c.3.6. Percent of parents participation in Brigada Eskwela from 90% to 100% by 2019. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Attendance Record |  |
|  | c.3.7. Four (4) private individuals and/or organizations/corporations donate to the school in a school year 2016-2019 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Deed of Donation |  |
| c.4. Resource mobilization efforts intensified | c.4.1. Resource mobilization efforts conducted |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Monitoring Report Financial report |  |
|  | Name of resource mobilization program | Yr 1 |  |  |  |  | Yr 2 |  |  |  |  |  |  | Yr 3 |  |  |  |  |  |  |  |  |  |  |  |
|  | MR. & MS. NUTRITION 2016 |  |  |  |  |  |  |  |  |  |  |  |  | P |  |  |  |  |  |  |  |  |  |  |  |
|  |  | P |  |  |  |  | P |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | MR. & MS. UN |  |  |  |  |  |  |  |  |  |  |  |  | P |  |  |  |  |  |  |  |  |  |  |  |
|  |  | P |  |  |  |  | P |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | King and Queen of hearts |  |  |  |  |  |  |  |  |  |  |  |  | P |  |  |  |  |  |  |  |  |  |  |  |
|  |  | P |  |  |  |  | P |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| c.5. Improved School Environment | c.5.1. Number of conflicts r educed |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Logbook |  |
|  | Conflict | Baseline |  |  |  |  | Yr 1 |  |  |  |  |  |  | Yr 2 |  |  |  |  |  |  | Yr 3 |  |  |  |  |
|  | Pupil– pupil |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | conflict | 2 |  |  |  |  | 0 |  |  |  |  |  |  | 0 |  |  |  |  |  |  | 0 |  |  |  |  |
|  | Teacher – pupil |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | conflict | 0 |  |  |  |  | 0 |  |  |  |  |  |  | 0 |  |  |  |  |  |  | 0 |  |  |  |  |
|  | Teacher – teacher |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | conflict | 0 |  |  |  |  | 0 |  |  |  |  |  |  | 0 |  |  |  |  |  |  | 0 |  |  |  |  |
|  | Teacher – |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | parent conflict | 0 |  |  |  |  | 0 |  |  |  |  |  |  | 0 |  |  |  |  |  |  | 0 |  |  |  |  |
| D. School Performance Indicators |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| d.1. Improved School Performance Indicators | d.1.1. Decreased simple dropout rate from 2.74% to1% by 2019. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Form 18 Form 18 Form 18 Form 18 |  |
|  | d.1.2. Decreased failure rate from 8 to1 % by 2019. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | d.1.3. Maintained graduation rate of 100% until 2019. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | d.1.4. Decreased repetition rate from 8.17%to 1 % by 2019 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

SCHOOL PRIORITY IMPROVEMENT AREAS

Area:  PROVISION OF EQUITABLE ACCESS

| Stream | Suggested Interventions |
| --- | --- |
| 1. Needs two teachers for the school | Request for additional two teachers for the school |
| 2. Book-pupil ratios in all subject areas and grade levels are below the standard of 1:1 | Purchase textbooks in all subject areas and grade levels to make 1:1 book-pupil ratio |
| 3. Needs computer sets for instructional purposes | Purchase computer units for instructional purposes |
| 4. Needs tools and equipment in EPP (home economics, industrial arts and agriculture/gardening) | Purchase tools and equipment for EPP |
| 5. Needs additional facilities(i.e. Computer laboratory, Home economics room, perimeter fence and school nursery) | Request for construction of new facilities to school |
| 6. Six instructional classrooms and the existing perimeter fence need immediate repair | Request for funds and materials for the repair of 6 instructional rooms and perimeter fence |
| 7. Solar panel needed to reduce electricity expenditures | Request for funding from LGU or ask from grant in the international renewable energy corporations |

Area: QUALITY AND RELEVANCE OF BASIC EDUCATION

|  | Stream | Suggested Interventions |
| --- | --- | --- |
| 1. | 29.5% of pupils are independent readers which is below the standard of 100% | Implement |
| 2. | Performance level in NAT is below the standard of 75% | Organize review classes in all subject areas and grade levels starting November to January. |
| 3. | 49% of Grade I entrants have ECD | Encourage parents to enroll their school age children to pre-school before they can be accepted to Grade I |
| 4. | Nine of 10 teachers are computer literate | Conduct INSET in computer literacy |
| 5. | Zero teachers conducted action research in a year | Encourage teachers to conduct one action research in a year |
| 6. | 31% of pupils have normal BMI | Implements feeding program for 6 sustained months |

Area: SCHOOL MANAGEMENT

|  | Stream | Suggested Interventions |
| --- | --- | --- |
| 1. | 70% of parents participates in Brigada Eskwela, attend assemblies and meetings in a year | Implement food for work in Brigada Eskwela, supplemented by the QUEEN program |
| 2. | Zero alumni association has been organized | Organize one functioning alumni association in the school |
| 3. | Barangay has allocated funds for the school and will be allocating again | Lobby to the barangay council to allocate funds for the next school projects |
| 4. | 49% of Grade I entrants have ECD | Encourage parents to enroll their school age children to pre-school before they can be accepted to Grade I |
| 5. | Nine of 10 teachers are computer literate | Conduct INSET in computer literacy |
| 6. | Zero teachers conducted action research in a year | Encourage teachers to conduct one action research in a year |
| 7. | 31% of pupils have normal BMI | Implements feeding program for 6 sustained months |

School Improvement Plan

Cambitala Elementary School

School Year 2016-2019

PROGRAMS AND ACTION PLANS

# 3-Year Work and Financial Plan

| Programs/Projects | Objectively Verifiable Indicators |  | Means of Verification | Physical Targets |  |  |  | Financial Targets |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  | Year 1 | Year 2 | Year 3 |
|  |  |  |  | Year 1 | Year 2 | Year 3 | Amount | Amount | Amount |
| Goal |  |  |  |  |  |  |  |  |  |
| Improved school performance in the Division of Nueva Ecija |  |  |  |  |  |  |  |  |  |
| Purpose |  |  |  |  |  |  |  |  |  |
| Improved student and school performance of Cambitala Elementary School | BY 2019 overall pupils/students achievement increased from 71.24% to 77% |  | NAT Result | 73% | 75% | 77% |  |  |  |
|  | By 2019 pupils/students achievement increased in the following subjects: |  |  |  |  |  |  |  |  |
|  | Subjects | Baseline |  |  |  |  |  |  |  |
|  | Science | 71.18% |  | 73% | 75% | 77% |  |  |  |
|  | English | 75% |  | 76% | 77% | 78% |  |  |  |
|  | Mathematics | 53.14% |  | 58% | 63% | 75.10% |  |  |  |
|  | Filipino | 86.96% |  | 88% | 89% | 90% |  |  |  |
|  | Araling Panlipunan | 69.90% |  | 72% | 74% | 77% |  |  |  |
| CONTRIBUTORY OBJECTIVES |  |  |  |  |  |  |  |  |  |
| A. Provision of Equitable Access |  |  |  |  |  |  |  |  |  |
| a.1. hired competent and adequate teaching & non-teaching personnel | a.1.1. Two (2) teaching |  | Approved Appointment Papers |  |  |  |  |  |  |
|  | ► Guidance |  |  |  |  |  |  |  |  |
|  | Counselor |  |  | 0 | 0 | 0 |  |  |  |
|  | ► Librarian |  |  | 0 | 0 | 0 |  |  |  |
|  | ► Teacher |  |  | 1 | 0 | 0 |  |  |  |
|  | ► Pre-school Teacher |  |  | 1 | 0 | 0 |  |  |  |
| a.2. Improved availability of Instructional and learning materials | a.2.1. Procured the following materials: |  |  |  |  |  |  |  |  |
|  | Equipment |  | Delivery |  |  |  |  |  |  |
|  |  |  | Receipt |  |  |  |  |  |  |
|  | Computers |  | Inspection Report | 6units | 0 | 0 | 120,000. 00 |  |  |
|  | Industrial Arts |  |  |  |  |  |  |  |  |
|  | Hammer |  |  | 1 | 1 | 1 | 150.0 0 | 150.0 0 | 150.0 0 |
|  | Saw |  |  | 1 | 1 | 1 | 150.0 0 | 150.0 0 | 150.0 0 |
|  | Tape measure |  |  | 1 | 1 | 1 | 300.0 | 300.0 | 300.0 |
|  |  |  |  |  |  |  | 0 | 0 | 0 |
|  | Home Economics |  |  |  |  |  |  |  |  |
|  | Sewing machine |  |  | 3 | 0 | 0 | 180,000. 00 |  |  |
|  | Oven |  |  | 1 | 0 | 0 | 20,000. 00 |  |  |
|  | LPG tank |  |  | 1 | 0 | 0 | 2,000.0 0 |  |  |
|  | Agriculture/Gardening tools |  |  |  |  |  |  |  |  |
|  | Rake |  |  | 4 | 0 | 0 | 2,000.0 0 |  |  |
|  | Spade |  |  | 2 | 0 | 1 | 800.0 0 |  | 400.0 0 |
|  | Hoe |  |  | 4 | 0 | 0 | 2,000.0 0 |  |  |
|  | Sprinkler |  |  | 5 | 0 | 0 | 1,000.0 0 |  |  |
|  | Bolo |  |  | 5 | 0 | 0 | 1,000.0 0 |  |  |
|  | Others |  |  |  |  |  |  |  |  |
|  | Tents |  |  | 4 | 0 | 0 | 40,000. 00 |  |  |
|  | Water Dispenser |  |  | 2 | 0 | 2 | 8,000.0 0 |  | 53,000.0 0 |
|  | Solar panel |  |  | 1 | 1 | 1 | 45 |  |  |
|  | a.2.2. Procured/accepted the following textbooks to achieve 1:1 textbook pupil/student ratio |  |  |  |  |  |  |  |  |
|  | English |  |  |  |  |  |  |  |  |
|  | Grade 1 |  |  | 123 | 0 | 0 | 30,750. 00 |  |  |
|  | Grade 2 |  |  | 84 | 0 | 0 | 21,000. |  |  |
|  |  |  |  |  |  |  | 00 |  |  |
|  | Grade 3 |  | Delivery Receipt | 62 | 0 | 0 | 15,500. 00 |  |  |
|  | Grade 4 |  | Inspection Report | 79 | 0 | 0 | 19,750. 00 |  |  |
|  | Grade 5 |  |  | 56 | 0 | 0 | 14,000. 00 |  |  |
|  | Grade 6 |  |  | 71 | 0 | 0 | 17,750. 00 |  |  |
|  | Science |  |  |  |  |  | - |  |  |
|  | Grade 3 |  |  | 67 | 0 | 0 | 16,750. 00 |  |  |
|  | Grade 4 |  |  | 92 | 0 | 0 | 23,000. 00 |  |  |
|  | Grade 5 |  |  | 68 | 0 | 0 | 17,000. 00 |  |  |
|  | Grade 6 |  |  | 84 | 0 | 0 | 21,000. 00 |  |  |
|  | Filipino |  |  |  |  |  | - |  |  |
|  | Grade 1 |  |  | 137 | 0 | 0 | 34,250. 00 |  |  |
|  | Grade 2 |  |  | 90 | 0 | 0 | 22,500. 00 |  |  |
|  | Grade 3 |  |  | 85 | 0 | 0 | 21,250. 00 |  |  |
|  | Grade 4 |  |  | 87 | 0 | 0 | 21,750. 00 |  |  |
|  | Grade 5 |  |  | 49 | 0 | 0 | 12,250. 00 |  |  |
|  | Grade 6 |  |  | 87 | 0 | 0 | 21,750. 00 |  |  |
|  | Math |  |  |  |  |  | - |  |  |
|  | Grade 1 |  |  | 108 | 0 | 0 | 27,000. 00 |  |  |
|  | Grade 2 |  |  | 67 | 0 | 0 | 16,750. 00 |  |  |
|  | Grade 3 |  |  | 77 | 0 | 0 | 19,250. 00 |  |  |
|  | Grade 4 |  |  | 51 | 0 | 0 | 12,750. 00 |  |  |
|  | Grade 5 |  |  | 45 | 0 | 0 | 11,250. 00 |  |  |
|  | Grade 6 |  |  | 75 | 0 | 0 | 18,750. 00 |  |  |
|  | Sibika/HKS |  |  |  |  |  | - |  |  |
|  | Grade 1 |  |  | 118 | 0 | 0 | 29,500. 00 |  |  |
|  | Grade 2 |  |  | 63 | 0 | 0 | 15,750. 00 |  |  |
|  | Grade 3 |  |  | 57 | 0 | 0 | 14,250. 00 |  |  |
|  | Grade 4 |  |  | 87 | 0 | 0 | 21,750. 00 |  |  |
|  | Grade 5 |  |  | 65 | 0 | 0 | 16,250. 00 |  |  |
|  | Grade 6 |  |  | 84 | 0 | 0 | 21,000. 00 |  |  |
|  | EPP |  |  |  |  |  | - |  |  |
|  | Grade 4 |  |  | 87 | 0 | 0 | 21,750. 00 |  |  |
|  | Grade 5 |  |  | 76 | 0 | 0 | 19,000. 00 |  |  |
|  | Grade 6 |  |  | 97 | 0 | 0 | 24,250. 00 |  |  |
|  | MSEP |  |  |  |  |  | - |  |  |
|  | Grade 4 |  |  | 87 | 0 | 0 | 21,750. 00 |  |  |
|  | Grade 5 |  |  | 76 | 0 | 0 | 19,000. 00 |  |  |
|  | Grade 6 |  |  | 97 | 0 | 0 | 24,250. 00 |  |  |
| a.3. Improved Physical | a.3.1. Constructed, |  |  |  |  |  |  |  |  |
| environment for learning | Accepted & Turned over the following facilities |  |  |  |  |  |  |  |  |
|  | IA shop |  | Actual facilities | 0 | 1 | 0 |  | 650,000. 00 |  |
|  | H.E |  | Certificate of Acceptance | 1 | 0 | 0 | 650,000. 00 |  |  |
|  | School Nursery |  |  | 1 | 0 | 0 | 100,000. 00 |  |  |
|  | Science lab |  |  | 0 | 0 | 1 |  |  | 650,000. 00 |
|  | Computer lab |  |  | 1 | 0 | 0 | 650,000. 00 |  |  |
|  | Perimeter fence |  |  | 60 m span | 50 m span | 40 m span |  |  |  |
|  | a.3.2. Repaired, accepted & turned over the following facilities: |  |  |  |  |  |  |  |  |
|  | Classrooms |  | Actual facilities | 6 | 4 | 2 | 300,000. 00 | 200,000. 00 | 100,000. 00 |
|  | Library |  | Certificate of Acceptance | 0 | 0 | 1 |  |  | 100,000. 00 |
|  | Computer Lab. |  |  | 0 | 0 | 1 |  |  | 100,000. 00 |
|  | a.3.3. School perimeter fence completed |  | Actual facilities | 80% | 90% | 100% | 50,000. 00 | 50,000. 00 | 50,000. 00 |
|  |  |  | Certificate of Acceptance |  |  |  |  |  |  |
| B. Quality and Relevance of Basic Education |  |  |  |  |  |  |  |  |  |
| b.1. Improved reading skills in | b.1.1. All students |  | Post Phil-Iri | 251 | 312 | 356 |  |  |  |
| English subjects | read within their standard reading level (independent readers) |  | Report |  |  |  |  |  |  |
| b.2. Improved skills of pupils IN SCIENCE, MATHEMATICS, HEKASI, | b.2.1. Organized review classes in all subjects and grade levels starting from November 2010 to February 2011 and the years thereafter |  | Monitoring Report | 13 classes | 13 classes | 13 classes |  |  |  |
|  |  |  | Class Record |  |  |  |  |  |  |
| b.3. Improved Curriculum Implementation and Instructional Delivery | b.3.1. 100% of school days met or delivered per year |  | FORM 2 |  |  |  |  |  |  |
|  | b.3.2. 100% of pupils are promoted considering the "no read, no move" principle of the Every Child a Reader Program (ECARP) |  | Form 18 | 100% | 100% | 100% |  |  |  |
|  | b.3.3. 100% of the Grade I entrants have ECD |  |  |  |  |  |  |  |  |
|  | experiences |  | Enrolment list | 100% | 100% | 100% |  |  |  |
|  | b.3.4. 100% of the Grade I Entrants have been positively considered under |  | SReA report | 100% | 100% | 100% |  |  |  |
|  | School Readiness |  |  |  |  |  |  |  |  |
| b.4. Improved subject knowledge/ teaching skills of teachers | b.4.1. Teachers were trained on results of NCBTS/TSNA |  | Attendance Sheet | 6 | 6 | 4 | 120,000. 00 | 120,000. 00 | 80,000. 00 |
|  |  |  | Training Completion Report |  |  |  |  |  |  |
|  | b.4.2. Teachers trained on computer literacy |  | Attendance Sheet | 2 | 2 | 2 | 50,000. 00 | 50,000. 00 | 50,000. 00 |
|  |  |  | Training Completion Report |  |  |  |  |  |  |
|  | • 10 out of 10 teachers subscribed to professional magazines |  | Subscription to professional magazines |  |  |  |  |  |  |
|  | • 10 out of 10 teachers are master’s degree holder |  | Diploma or special order | 5 | 9 | 14 |  |  |  |
|  | • 10 out of 10 teachers and Principal conducted one action research each a year |  | Copy of approved research proposal and recommendation | 15 | 15 | 15 | 30,000. 00 | 30,000. 00 | 30,000. 00 |
| b.5. Improved Nutritional status of pupils/students | b.5.1. 100% of students within normal status of nutrition |  | Report of Nutritional Status | 475 | 550 | 563 | 14,250. 00 | 16,500. 00 | 16,890. 00 |
|  | b.5.2. Feeding Program implemented in 6 sustained months |  | Monitoring Report | 6 months | 6 months | 6 months | 85,500. 00 | 99,000. 00 | 101,340. 00 |
| C. School Management |  |  |  |  |  |  |  |  |  |
| c.1. Instructional Supervision Strengthened | c.1.1. Frequency of supervision |  | Supervisory Report |  |  |  |  |  |  |
|  | School Principal |  |  | 10 out of 10 monthly | 10 out of 10 monthly | 10 out of 10 monthly |  |  |  |
|  | PSDS |  |  | 10 out of 10 quarterly | 10 out of 10 quarterly | 10 out of 10 quarterly |  |  |  |
|  | ES |  |  | 10 out of 10 /semester | 10 out of 10 /semester | 10 out of 10 /semester |  |  |  |
|  | c.1.2. Number of teacher supervised |  | Supervisory Report |  |  |  |  |  |  |
|  | School Head |  |  | 10 out of 10 monthly | 10 out of 10 monthly | 10 out of 10 monthly |  |  |  |
|  | PSDS |  |  | 10 out of 10/quarter | 10 out of 10/quarter | 10 out of 10 /quarter |  |  |  |
|  | ES |  |  | 10 of 10/semester | 10 of 10/semester | 10 of 10/semester |  |  |  |
| c.2. Effective School Management and Administration Implemented | c.2.1. 100% of teachers report to school on time. |  | Daily time Record |  |  |  |  |  |  |
|  | c.2.2. 100% of teachers have no more than 1 day absence in a month. |  | Daily time Record |  |  |  |  |  |  |
|  |  |  | Monitoring Report |  |  |  |  |  |  |
|  | c.2.3. 100% of the number of contact time observed by 2013 |  |  |  |  |  |  |  |  |
|  | c.2.4. 10 out of 10 teachers making home visits |  | Monitoring Report | 7 | 12 | 15 |  |  |  |
|  | c.2.5. PTA board conducts 10 meetings in a school year |  | Attendance Record |  |  |  |  |  |  |
|  |  |  |  | 10 | 10 | 10 |  |  |  |
|  |  |  | Record of minutes |  |  |  |  |  |  |
|  | c.2.6. One School Governing Council organized and made functional |  | Existence of SGC | 1 | 0 | 0 | 1,000.0 0 |  |  |
|  | c.2.7. Eight school INSET prepared and implemented. |  | Training Completion Report | 8 | 8 | 8 | 16,000. 00 | 16,000. 00 | 16,000. 00 |
| c.3. Stakeholders Participation Intensified | c.3.1. Parents attendance to PTA activities. Number of parents attended PTA meeting |  |  |  |  |  |  |  |  |
|  | Meeting |  | Attendance Sheet |  |  |  |  |  |  |
|  | Brigada Eskwela |  |  | 340 | 350 | 360 |  |  |  |
|  | General PTCA |  |  |  |  |  |  |  |  |
|  | Assembly |  |  | 300 | 330 | 360 |  |  |  |
|  | Homeroom PTCA |  |  | 300 | 330 | 360 |  |  |  |
|  | c.3.2. One (1) Alumni Association organized and made functional by 2011 |  | Constitution and By – Laws | 1 | 0 | 0 |  |  |  |
|  |  |  | Database is present |  |  |  |  |  |  |
|  | c.3.3. Increased financial investment by LGU’s. Amount invested by LGU’s |  | Financial Report |  |  |  |  |  |  |
|  | Source of | Yr 0 |  |  |  |  |  |  |  |
|  | funds |  |  |  |  |  |  |  |  |
|  | Brgy | 0 |  | 1% of Brgy. EdCom | 1% of Brgy. EdCom | 1% of Brgy. EdCom |  |  |  |
|  | Brgy. SK | 0 |  | 1% of S.P. | 1% of S.P. | 1% of S.P. |  |  |  |
|  | SEF | 67,48 2 |  | 100,000 | 150,000 | 200,000 |  |  |  |
|  | c.3.4. Increased financial investment by PTCA. Amount |  |  |  |  |  |  |  |  |
|  | invested by PTCA |  |  |  |  |  |  |  |  |
|  | PTCA | Yr 1 | Financial Report |  |  |  |  |  |  |
|  | GPTCA | P 20,000 |  | P 20,000 | P 25,000 | P 25,000 |  |  |  |
|  | c.3.5. 100% of pupils are covered by the Insurance program |  | Database is present | 60% | 80% | 100% |  |  |  |
|  |  |  | Monitoring Report |  |  |  |  |  |  |
|  | c.3.6. Percent of parents participation in Brigada Eskwela from 90% to 100% by 2019. |  | Attendance Record | 100% | 100% | 100% |  |  |  |
|  | c.3.7. Four (4) private individuals and/or organizations/corporations donate to the school in a school year |  | Deed of Donation | 4 | 4 | 4 |  |  |  |
| c.4. Resource mobilization efforts intensified | c.4.1. Resource mobilization efforts conducted |  |  |  |  |  |  |  |  |
|  | Name of resource mobilization program |  | Monitoring Report |  |  |  |  |  |  |
|  | Mr. &Ms. Education |  | Financial report | P | P | P |  |  |  |
|  | Mr. &Ms. UN |  |  | P | P | P |  |  |  |
|  |  |  |  | P | P | P |  |  |  |
| c.5. Improved School Environment | c.5.1. Number of conflicts reduced |  |  |  |  |  |  |  |  |
|  | Conflict | Baseline | Logbook |  |  |  |  |  |  |
|  | Pupil– |  |  |  |  |  |  |  |  |
|  | pupil conflict | 2 |  | 0 | 0 | 0 |  |  |  |
|  | Teacher – |  |  |  |  |  |  |  |  |
|  | pupil conflict | 0 |  | 0 | 0 | 0 |  |  |  |
|  | Teacher – |  |  |  |  |  |  |  |  |
|  | teacher conflict | 0 |  | 0 | 0 | 0 |  |  |  |
|  | Teacher – |  |  |  |  |  |  |  |  |
|  | parent conflict | 0 |  | 0 | 0 | 0 |  |  |  |
| D. School Performance Indicators |  |  |  |  |  |  |  |  |  |
| d.1. Improved School Performance Indicators | d.1.1. Decreased simple dropout rate from 2.74% to 1% by 2013. |  | Form 18 | 2% | 1.50% | 1% |  |  |  |
|  | d.1.2. Decreased failure rate from 8 to1 % by 2013. |  | Form 18 | 5% | 3% | 1% |  |  |  |
|  | d.1.3. Maintained graduation rate of 100% until 2013. |  | Form 18 | 100% | 100% | 100% |  |  |  |
|  | d.1.4. Decreased repetition rate from 8.17%to 1% by 2013 |  | Form 18 | 5.50% | 3% | 1% |  |  |  |

ANNUAL IMPLEMENTATION PLAN

| Programs/ Projects/ Activities | Objectively Verifiable Indicators |  | Means of Verification |  |  |  |  |  | TIME FRAME |  |  |  |  |  |  |  |  |  |  |  |  |  | Resource Requirement s |  | Amount and Sources |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Person/s Responsible | Other Resources |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  | 2011 |  |  |  |  |  |  |  |  |  | 2012 |  |  |  |  |  | LGU | PTCA | DepEd | OTH ERS | TOTA L |
|  |  |  |  | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A |  |  |  |  |  |  |  |
| Goal |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Improved school performance in the Division of Naga City |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Purpose |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Improved student and school performance of San Isidro Elementary School | BY 2019 overall pupils/students achievement increased from 71.24% to 77% |  | NAT Result |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | By 2019 pupils/students achievement increased in the following subjects: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Subjects | Baseline |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Science | 71. 18% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | English | 75% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Mathematics | 53. 14% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Filipino | 86. 96% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Araling |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Panlipunan | 69.90% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

| CONTRIBUTORY OBJECTIVES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| A. Provision of Equitable Access |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| a.1. hired competent and adequate teaching | a.1.1. Two (2) teaching personnel hired |  | Approved Appointment Papers |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ▪ Prepare resolution of |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | SGC, SH |  |  |  |  |  |  |
| request to DepED |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| for needed ▪ submit resolution |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| to SDS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | SH |  |  |  |  |  |  |
| ▪ Make follow-up |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | SH |  |  |  |  |  |  |
| ▪ Publish notice of vacant position |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | HRMO | Publication |  | 10, 000.00 |  | 10, 000.00 |  |
| ▪ calls for ranking |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | PSB, SDS |  |  |  |  |  | - |
| ▪ appoints the |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| applicants |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | PSB, SDS |  |  |  |  |  | - |
| ▪ Hired teachers, guidance counselor and librarian |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 690, 200.00 |  | 690, 200.00 |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | SDS |  |  |  |  |  |  |
| a.2. Improved availability of Instructional and learning materials | a.2.1. Instructiona l and learning materials procured |  | Delivery Receipt |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 242, 000 | 7, 400 | 600, 000 | 8, 000.0 0 | 857, 400.0 0 |
|  |  |  | Inspection |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Report |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 600, 000 |  | 600, 000 |
| ▪ Prepare inventory of existing equipment. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | School Custodian |  |  |  |  |  | - |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 150.00 |  |  | 150.00 |
| ▪ prepare procurement plan |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | SH |  |  | 150.00 |  |  | 150.00 |
| ▪ canvass of prices |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | SH, Custodian |  |  | 300.00 |  |  | 300.00 |
| ▪ requests funds |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | SH |  |  |  |  |  | - |
| ▪ Publish notice to bid |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | SH, BAC | Publicaion | 180,000.00 |  |  |  | 180,000.00 |
| ▪ calls for bidding |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | SH, BAC |  | 20,000.00 |  |  |  | 20,000.00 |
| ▪ makes orders |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | SH, BAC |  | 2,000.00 |  |  |  | 2,000.00 |
| ▪ receives supplies |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | SH, Custodian |  |  |  |  |  |  |
|  | a.2.2. Procured/accepted the following textbooks to achieve 1:1 textbook pupil/student ratio |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 450,000.00 | - | 250, 500 | - | 700,500.00 |
| ▪ Prepare inventory of existing materials. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | School Property Custodian |  |  |  |  |  |  |
| ▪ prepare |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| procurement plan |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | SH |  |  |  |  |  |  |
| ▪ canvass of prices |  |  | Delivery Receipt |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | SH, Custodian |  |  |  | 1,000.00 |  | 1,000.00 |
| ▪ requests funds |  |  | Inspection Report |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | SH |  |  |  |  |  | - |
| ▪ Publish notice to bid |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | SH, BAC | Publication |  |  | 10, 000 |  | 10, 000.00 |
| ▪ calls for bidding |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | SH, BAC |  |  |  | 5, 000.00 |  | 5, 000.00 |
| ▪ makes orders |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | SH, BAC |  |  |  |  |  |  |
| ▪ receives supplies |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | SH, Custodian |  | 450, 000 | - | 234, 500 | - | 684, 500.00 |
| a.3. Improved Physical environment for learning | a.3.1. Constructed , Accepted & Turned over the following facilities: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ▪ Prepare requests for additional facilities | H.E |  | Actual facilities |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 650, 000 |  | 650, 000.00 |
| ▪ Submits requests for additional facilities | School Nursery |  | Certificate of Acceptance |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | SH |  | 100,000 |  |  |  | 100, 000.0 0 |
| ▪ requests funds | Computer lab |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | SH |  |  |  | 650, 000 |  | 650, 000.00 |
| ▪ Publish notice to bid | Perimeter fence |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | BAC | Publication | 100, 000 |  |  |  | 100, 000.0 0 |
| ▪ calls for bidding |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | BAC, SH |  |  | 5, 000 |  |  | 5, 000.00 |
| ▪ awards the |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| project |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | BAC |  |  |  |  |  | - |
| ▪ construction of projects |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Contractor |  |  |  |  |  | - |
| ▪ turn-over and |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | SH, DPFC |  |  |  |  |  |  |
| acceptance of facilitates |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |
|  | a.3.2. Repaired, accepted & turned over the following facilities: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ▪ Prepare requests for repair of faciltities | Classrooms |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 100, 000.00 |  | 200, 000 |  | 300, 000.00 |
| ▪ Submits requests for repair of facilities | Library |  | Actual facilities |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | SH |  |  |  |  |  | - |
| ▪ requests funds | Computer Lab. |  | Certificate of Acceptance |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | SH |  |  |  |  |  | - |
| ▪ Publish notice to bid |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | BAC | Publication | 10,000.00 |  |  |  | 10, 000.00 |
| ▪ calls for bidding |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | BAC, SH |  |  | 5, 000 |  |  | 5, 000.00 |
| ▪ awards the |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| project |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | BAC |  |  |  |  |  | - |
| ▪ construction of projects |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Contractor |  |  |  |  |  | - |
| ▪ turn-over and |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| acceptance of facilitites |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | SH, DPFC |  |  |  |  |  | - |
|  | a.3.3. School perimeter fence |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | completed |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ▪ Prepare requests for additional faciltities |  |  | Actual facilities |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 50, 000.00 |  |  |  | 50, 000.00 |
| ▪ Submits requests for additional facilities |  |  | Certificate of Acceptance |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | SH |  |  |  |  |  | - |
| ▪ requests funds |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | SH |  |  |  |  |  | - |
| ▪ Publish notice to bid |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | BAC | Publication | 10, 000.00 |  |  |  | 10, 000.00 |
| ▪ calls for bidding |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | BAC, SH |  |  | 5, 000 |  |  | 5, 000.00 |
| ▪ awards the |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| project |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | BAC |  |  |  |  |  | - |
| ▪ construction of projects |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Contractor |  |  |  |  |  | - |
| ▪ turn-over and |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| acceptance of facilitites |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | SH, DPFC |  |  |  |  |  | - |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |
| B. Quality and Relevance of Basic |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Education |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |
| b.1. Improved reading skills in English subjects | b.1.1. All students read within their |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |
|  |  |  | Post Phil-Iri Report |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |
|  | standard reading level |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |
| ▪ Prepare proposal for reading |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| intervention |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | SH |  |  |  |  |  | - |
| ▪ Submits proposal for |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| approval |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | SH |  |  |  |  |  | - |
| ▪ Reproduce reading materials |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Adviser s |  |  | 5, 000 | 5, 000.00 |  | 10, 000.00 |
| ▪ Implement reading |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| intervention to all classes |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | SH, Advisers |  |  |  |  |  | - |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |
| b.2. Improved skills of pupils in Science, Mathematics, Filipino and MAKABAYAN | b.2.1. Organized review classes in all subjects and grade levels starting from November 2010 to February 2011 and the years thereafter |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |
|  |  |  | Monitoring Report |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |
|  |  |  | Class Record |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |
| ▪ Prepare proposal For review /remedial classes |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | SH |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |
| ▪ Submits proposal for approval |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | SH |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |
| ▪ Reproduce instructional materials |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | SH |  |  | 5, 000 | 5, 000.00 |  | 10, 000.00 |
| ▪ Implement review instructions to all classes |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | SH,, ADVISERS |  |  |  |  |  | - |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |
| b.3. Improved Curriculum Implementation and Instructional Delivery | b.3.1. 100% of school days met or delivered per year |  | FORM 2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |
|  | b.3.2. 100% of pupils are promoted considering the "no read, no move" principle of the Every Child a Reader Program (ECARP) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Form 18 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |
| ▪ Closely supervise class instructions |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | SH |  |  |  |  |  | - |
| ▪ Personally conduct reading test to pupils |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | SH |  |  |  |  |  | - |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |
| ▪ Prepare list of pre-school graduates | b.3.3. 100% of the Grade I entrants have ECD experiences |  | Enrolment list |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | SH |  |  |  |  |  | - |
| ▪ Closely supervise enrolment of |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| grade I entrants |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | SH |  |  |  |  |  | - |
| ▪ Closely supervise conduct of SReA testing to Grade I entrants | b.3.4. 100% of the Grade I Entrants have been positively considered under School Readiness Assessment |  | SReA report |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | SH, Advisers |  |  |  |  |  | - |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |
| b.4. Improved subject knowledge/ teaching skills of teachers | b.4.1. Teachers were trained on results of NCBTS/TSNA |  | Attendance Sheet |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |
|  |  |  | Training Completion Report |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |
| ▪ Teachers prepare TSNA & IPPD | b.4.2. Teachers trained on computer literacy |  | Attendance Sheet |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Teachers |  |  |  |  |  | - |
| ▪ Prepare |  |  | Training |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | SH |  |  |  |  |  |  |
| summary list of needs based from IPPD |  |  | Completion Report |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |
| ▪ Prepare summary list of needs based from |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| TSNA |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | SH |  |  |  |  |  | - |
| ▪ Conducts INSET based from needs |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | SH,, Teachers |  | 100, 000.00 |  | 100, 000 |  | 200, 000.00 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |
| ▪ Encourage teachers to subscribe to professional mags | • 14 out of 14 teachers subscribed to professional magazines |  | Subscription to professional magazines |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | SH |  |  |  |  |  | - |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |
| ▪ Receives magazines from publishers |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Teachers |  |  |  |  | 50, 000.00 | 50, 000.00 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |
| ▪ Encourage teachers to finish graduate school | • 14 out of 14 teachers are master’s degree holder |  | Diploma or special order |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | SH |  |  |  |  |  | - |
| ▪ Teachers enroll to HEIs |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Teachers |  |  |  |  | 200, 000.00 | 200, 000.00 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |
| ▪ Conducts INSET on Action Research | • 14 out of 14 teachers and Principal |  | Copy of approved research proposal and |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | SH, Teachers |  | 10, 000.00 | 5, 000 |  |  | 15, 000.00 |
|  | conducted one action research each a year |  | recommendation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ▪ Encourage teachers to |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| prepare proposals |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | SH |  |  |  |  |  | - |
| ▪ Submits proposals for approval |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | SH, Teachers |  |  |  |  | 2, 000.00 | 2, 000.00 |
| ▪ Conducts the research |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Teachers |  |  | 5, 000 | 5, 000.00 | 5, 000.00 | 15, 000.00 |
| ▪ Prepare the research data and interpretation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Teachers |  |  |  |  | 3, 000.00 | 3, 000.00 |
| ▪ Submits the results for adoption |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Teachers, SH |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |
| b.5. Improved Nutritional status of pupils/students | b.5.1. 100% of students within normal status of nutrition |  | Report of Nutritional Status |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |
| ▪ Measure pupils' height and weight | b.5.2. Feeding Program implemented in 6 sustained months |  | Monitoring Report |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | SH, Nutri Coord |  |  |  |  |  | - |
| ▪ prepare list of pupils with below normal status |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Nutri Coord |  |  |  |  |  | - |
| ▪ Lobby to LGU for |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| support |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | SH |  |  |  |  |  | - |
| ▪ Implements feeding program |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | SH, Nutri Coord |  | 80, 000.00 | 5, 000 0 |  | 5, 000.00 | 90, 000.00 |
| C. School Management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |
| c.1. Instructional Supervision Strengthened | c.1.1. Supervisors conducts at least 14 supervisions: |  | Supervisory Report |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |
|  | School Principal per month |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | SH |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |
|  | PSDS per quarter |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | PSDS |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |
|  | Ess per |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | EPSs |  |  |  |  |  |  |
|  | semester |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |
|  | c.1.2. 14teacher supervised by |  | Supervisory Report |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |
|  | School Principal per month |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | SH |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |
|  | PSDS per quarter |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | PSDS |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |
|  | Ess per semester |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | EPSs |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |
| c.2. Effective School Management and | c.2.1. 100% of teachers report to school on time. |  | Daily time Record |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Teachers |  |  |  |  |  | - |
| Administration |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Implemented |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |
|  | c.2.2. 100% of teachers have no more than 1 day absence in a month. |  | Daily time Record |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Teachers |  |  |  |  |  | - |
|  |  |  | Monitoring Report |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |
|  | c.2.3. 100% of the number of contact time observed by 2013 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Teachers, SH |  |  |  |  |  | - |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |
|  | c.2.4. 14 out of 14 teachers making home visits |  | Monitoring Report |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Teachers |  |  |  |  |  | - |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |
|  | c.2.5. PTA board conducts 10 meetings in a school year |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Attendance Record |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | PTA Board |  |  | 1, 000 |  |  | 1, 000.00 |
|  |  |  | Record of |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | minutes |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |
|  | c.2.6. One School Governing Council organized and made functional |  | Existence of SGC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |
| ▪ Prepares list of stakeholders in |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | SH |  |  |  |  |  |  |
| the SGC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |
| ▪ Calls for a meeting cum orientation of |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | SH |  |  |  |  |  |  |
| members |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |
| ▪ Conducts meeting and elect officers |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | SH, Stakeholders |  |  |  |  | 1, 000.00 | 1, 000.00 |
| ▪ Organizes the Supreme Pupil Government |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | SGC |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |
|  | c.2.7. Fifteen school INSET prepared and implemented. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |
| ▪ Prepare summary list of needs based from IPPD |  |  | Training Completion Report |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | SH |  |  |  |  |  | - |
| ▪ Prepare summary list of needs based from |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| TSNA |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | SH |  |  |  |  |  | - |
| ▪ Prepares |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| proposals for INSETs for 8 months |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | SH, Coordinators |  |  |  |  |  | - |
| ▪ Seek approval |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | SH |  |  |  |  |  |  |
| for the proposed |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| INSET |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |
| ▪ Lobby for fund |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| support |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | SH |  |  |  |  |  | - |
| ▪ Conducts INSET based from needs |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | SH, Teachers |  | 20, 000.00 |  | 10, 000 | 10, 000.00 | 40, 000.00 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |
| c.3. Stakeholders Participation Intensified | c.3.1. Parents attendance to PTA activities increased |  | Attendance Sheet |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |
| ▪ Intensify IEC activities |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | SH, PTA Board |  |  |  |  |  | - |
| ▪ Lobby for |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| support for PTA activities |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | SH, PTA Board |  |  |  |  |  | - |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |
|  | c.3.2. One (1) Alumni Association organized and made functional by 2011 |  | Constitution and By – Laws |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |
|  |  |  | Database is present |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |
| ▪ Prepare proposals for alumni |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| homecoming |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | SH |  |  |  |  |  | - |
| ▪ Conducts meeting and create TWG |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | SH, Alumni reps |  |  |  |  |  | - |
| ▪ TWG finalizes activities for |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | TWG |  |  |  |  |  | - |
| homecoming |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ▪ Conducts IEC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| activities for the homecoming |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | SH, TWG, Teachers |  |  |  |  |  | - |
| ▪ Conducts alumni homecoming |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | TWG |  |  |  |  | 5, 000.00 | 5, 000.00 |
| ▪ Organizes |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| alumni association |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Alumni |  |  |  |  |  | - |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |
|  | c.3.3. Increased financial investment by LGU’s. Amount invested by LGU’s |  | Financial Report |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |
| ▪ Prepare budget |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| proposals |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | SH |  |  |  |  |  | - |
| ▪ Seek approval of |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| budget proposals |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | SH |  |  |  |  |  | - |
| ▪ Lobby to barangay council during budget |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| hearing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | SH |  |  |  |  |  | - |
| ▪ Inclusion of |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Brgy. Council |  |  |  |  |  |  |
| school projects to barangay budget |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |
|  | c.3.4. Increased financial investment by PTCA. Amount |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |
|  | invested by PTCA |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ▪ Submit project proposal to PTA for adoption | PTCA | Yr 1 | Financial Report |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | SH |  |  |  |  |  | - |
| ▪ PTA adopts school project | GPTC A | P 20, 000 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | PTA Board |  |  |  |  |  | - |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |
| ▪ Intensify IEC activities | c.3.5. 100% of pupils are covered by the QUEEN program |  | Database is present |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | SH, PTA |  |  |  |  |  | - |
| ▪ Lobby for support for PTA activities |  |  | Monitoring Report |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | SH, PTA |  |  |  |  |  | - |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |
| ▪ Intensify IEC activities | c.3.6. Percent of parents participation in Brigada Eskwela from 90% to 100% by 2013. |  | Attendance Record |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | SH, PTA |  |  |  |  |  | - |
| ▪ Lobby for support for PTA activities |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | SH, PTA |  |  |  |  |  | - |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |
|  | c.3.7. Four (4) private individuals and/or organizations/corporations donate to the school in a school year. |  | Deed of Donation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |
| ▪ Prepare project |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| proposals |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | SH |  |  |  |  |  |  |
| ▪ Seek approval of |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| budget proposals |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | SH |  |  |  |  |  |  |
| ▪ Lobby to individuals /organization |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| corporations |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | SH |  |  |  |  |  |  |
| ▪ Receives |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| donation to school |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | SH |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |
| c.4. Resource mobilization efforts intensified | c.4.1.Resource mobilization efforts conducted |  | Monitoring Report |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |
|  |  |  | Financial report |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ▪ Prepare project proposals |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | SH, Coordinator |  |  |  |  |  |  |
| ▪ Seek approval of budget proposals |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | SH, Coordinator |  |  |  |  |  |  |
| ▪ Implements projects |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Coordinator |  |  |  |  |  |  |
| ▪ Receives |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| donation to school |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | SH |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |
| c.5. Improved School Environment | c.5.1. Number of conflicts reduced |  | Logbook |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |

| D. School |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Performance |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Indicators |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |
| d.1. Improved School Performance Indicators | d.1.1. Decreased simple dropout rate from 2.74% to 2% | Form 18 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |
|  | d.1.2. Decreased failure rate from 8 to 5%. | Form 18 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |
|  | d.1.3. Maintained graduation rate of 100%. | Form 18 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |
|  | d.1.4. Decreased repetition rate from 8.17% to 5.5%. | Form 18 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |

MONITORING AND EVALUATION PLAN

| Contributory Objectives | PHYSICAL |  |  |  |  |  |  |  |  | FINANCIAL |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Year 1 |  |  | Year 2 |  |  | Year 3 |  |  | Year 1 |  |  | Year 2 |  |  | Year 3 |  |  |
|  | Target | Actual | % Acmp | Target | Actual | % Acmp | Target | Actual | % Acmp | Target | Actual | % Accmp | Target | Actual | % Accmp | Target | Actual | % Accmp |
| A. Provision of Equitable Access |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| a.1.hired competent and adequate teaching personnel |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Guidance |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Counselor | 0 |  |  | 0 |  |  | 0 |  |  |  |  |  |  |  |  |  |  |  |
| Librarian | 0 |  |  | 0 |  |  | 0 |  |  |  |  |  |  |  |  |  |  |  |
| Teacher | 1 |  |  | 0 |  |  | 0 |  |  |  |  |  |  |  |  |  |  |  |
| Pre-school Teacher | 1 |  |  | 0 |  |  | 0 |  |  |  |  |  |  |  |  |  |  |  |
| a.2. Improved availability of Instructional and learning materials |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| a.2.1. Procured the following materials: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Equipment |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Computers | 6 units |  |  | 0 |  |  | 0 |  |  | 120,000.00 |  |  |  |  |  |  |  |  |
| Industrial Arts |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Hammer | 1 |  |  | 1 |  |  | 1 |  |  | 150 .00 |  |  | 150 .00 |  |  | 150 .00 |  |  |
| Saw | 1 |  |  | 1 |  |  | 1 |  |  | 150 .00 |  |  | 150 .00 |  |  | 150 .00 |  |  |
| Tape measure | 1 |  |  | 1 |  |  | 1 |  |  | 300 .00 |  |  | 300 .00 |  |  | 300 .00 |  |  |
| Home Economics |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sewing machine | 3 |  |  | 0 |  |  | 0 |  |  | 180,000.00 |  |  |  |  |  |  |  |  |
| Oven | 1 |  |  | 0 |  |  | 0 |  |  | 20,000.00 |  |  |  |  |  |  |  |  |
| LPG tank | 1 |  |  | 0 |  |  | 0 |  |  | 2,000.00 |  |  |  |  |  |  |  |  |
| Agriculture/ Gardening tools |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Rake | 4 |  |  | 0 |  |  | 0 |  |  | 2,000.00 |  |  |  |  |  |  |  |  |
| Spade | 2 |  |  | 0 |  |  | 1 |  |  | 800 .00 |  |  |  |  |  | 400 .00 |  |  |
| Hoe | 4 |  |  | 0 |  |  | 0 |  |  | 2,000.00 |  |  |  |  |  |  |  |  |
| Sprinkler | 5 |  |  | 0 |  |  | 0 |  |  | 1,000.00 |  |  |  |  |  |  |  |  |
| Bolo | 5 |  |  | 0 |  |  | 0 |  |  | 1,000.00 |  |  |  |  |  |  |  |  |
| Others |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Tents | 4 |  |  | 0 |  |  | 0 |  |  | 40,000.00 |  |  |  |  |  |  |  |  |
| Water Dispenser | 2 |  |  | 0 |  |  | 2 |  |  | 8,000.00 |  |  |  |  |  | 8,000.00 |  |  |
| Solar Panel | 1 |  |  | 1 |  |  | 1 |  |  |  |  |  |  |  |  |  |  |  |
| a.2.2.Procured/accepted the following textbooks to achieve 1:1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| textbook pupil |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| English |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Grade 1 | 123 |  |  | 0 |  |  | 0 |  |  | 30,750.00 |  |  |  |  |  |  |  |  |
| Grade 2 | 84 |  |  | 0 |  |  | 0 |  |  | 21,000.00 |  |  |  |  |  |  |  |  |
| Grade 3 | 62 |  |  | 0 |  |  | 0 |  |  | 15,500.00 |  |  |  |  |  |  |  |  |
| Grade 4 | 79 |  |  | 0 |  |  | 0 |  |  | 19,750.00 |  |  |  |  |  |  |  |  |
| Grade 5 | 56 |  |  | 0 |  |  | 0 |  |  | 14,000.00 |  |  |  |  |  |  |  |  |
| Grade 6 | 71 |  |  | 0 |  |  | 0 |  |  | 17,750.00 |  |  |  |  |  |  |  |  |
| Science |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  |  |
| Grade 3 | 67 |  |  | 0 |  |  | 0 |  |  | 16,750.00 |  |  |  |  |  |  |  |  |
| Grade 4 | 92 |  |  | 0 |  |  | 0 |  |  | 23,000.00 |  |  |  |  |  |  |  |  |
| Grade 5 | 68 |  |  | 0 |  |  | 0 |  |  | 17,000.00 |  |  |  |  |  |  |  |  |
| Grade 6 | 84 |  |  | 0 |  |  | 0 |  |  | 21,000.00 |  |  |  |  |  |  |  |  |
| Filipino |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  |  |
| Grade 1 | 137 |  |  | 0 |  |  | 0 |  |  | 34, 250.00 |  |  |  |  |  |  |  |  |
| Grade 2 | 90 |  |  | 0 |  |  | 0 |  |  | 22, 500.00 |  |  |  |  |  |  |  |  |
| Grade 3 | 85 |  |  | 0 |  |  | 0 |  |  | 21, 250.00 |  |  |  |  |  |  |  |  |
| Grade 4 | 87 |  |  | 0 |  |  | 0 |  |  | 21,750.00 |  |  |  |  |  |  |  |  |
| Grade 5 | 49 |  |  | 0 |  |  | 0 |  |  | 12,250.00 |  |  |  |  |  |  |  |  |
| Grade 6 | 87 |  |  | 0 |  |  | 0 |  |  | 21,750.00 |  |  |  |  |  |  |  |  |
| Math |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  |  |
| Grade 1 | 108 |  |  | 0 |  |  | 0 |  |  | 27, 000.00 |  |  |  |  |  |  |  |  |
| Grade 2 | 67 |  |  | 0 |  |  | 0 |  |  | 16, 750.00 |  |  |  |  |  |  |  |  |
| Grade 3 | 77 |  |  | 0 |  |  | 0 |  |  | 19, 250.00 |  |  |  |  |  |  |  |  |
| Grade 4 | 51 |  |  | 0 |  |  | 0 |  |  | 12, 750.00 |  |  |  |  |  |  |  |  |
| Grade 5 | 45 |  |  | 0 |  |  | 0 |  |  | 11, 250.00 |  |  |  |  |  |  |  |  |
| Grade 6 | 75 |  |  | 0 |  |  | 0 |  |  | 18, 750.00 |  |  |  |  |  |  |  |  |
| Sibika/HKS |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  |  |
| Grade 1 | 118 |  |  | 0 |  |  | 0 |  |  | 29, 500.00 |  |  |  |  |  |  |  |  |
| Grade 2 | 63 |  |  | 0 |  |  | 0 |  |  | 15, 750.00 |  |  |  |  |  |  |  |  |
| Grade 3 | 57 |  |  | 0 |  |  | 0 |  |  | 14, 250.00 |  |  |  |  |  |  |  |  |
| Grade 4 | 87 |  |  | 0 |  |  | 0 |  |  | 21, 750.00 |  |  |  |  |  |  |  |  |
| Grade 5 | 65 |  |  | 0 |  |  | 0 |  |  | 16, 250.00 |  |  |  |  |  |  |  |  |
| Grade 6 | 84 |  |  | 0 |  |  | 0 |  |  | 21, 000.00 |  |  |  |  |  |  |  |  |
| EPP |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  |  |
| Grade 4 | 87 |  |  | 0 |  |  | 0 |  |  | 21,750.00 |  |  |  |  |  |  |  |  |
| Grade 5 | 76 |  |  | 0 |  |  | 0 |  |  | 19,000.00 |  |  |  |  |  |  |  |  |
| Grade 6 | 97 |  |  | 0 |  |  | 0 |  |  | 24,250.00 |  |  |  |  |  |  |  |  |

| MSEP |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Grade 4 | 87 |  |  | 0 |  |  | 0 |  |  | 21,750.00 |  |  |  |  |  |  |  |  |
| Grade 5 | 76 |  |  | 0 |  |  | 0 |  |  | 19,000.00 |  |  |  |  |  |  |  |  |
| Grade 6 | 97 |  |  | 0 |  |  | 0 |  |  | 24,250.00 |  |  |  |  |  |  |  |  |
| a.3. Improved Physical environment for learning |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| a.3.1. Constructed, Accepted & Turned over the following facilities |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 0 |  |  | 1 |  |  | 0 |  |  |  |  |  | 650,000.00 |  |  |  |  |  |
| H.E | 1 |  |  | 0 |  |  | 0 |  |  | 650,000.00 |  |  |  |  |  |  |  |  |
| School Nursery | 1 |  |  | 0 |  |  | 0 |  |  | 100,000.00 |  |  |  |  |  |  |  |  |
| Science lab | 0 |  |  | 0 |  |  | 1 |  |  |  |  |  |  |  |  | 650,000.00 |  |  |
| Computer lab | 1 |  |  | 0 |  |  | 0 |  |  | 650,000.00 |  |  |  |  |  |  |  |  |
| Perimeter fence | 60 m span |  |  | 50 m span |  |  | 40 m span |  |  | 100,000.00 |  |  |  |  |  |  |  |  |
| a.3.2. Repaired, accepted & turned over the following facilities: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Classrooms | 6 |  |  | 4 |  |  | 2 |  |  | 300,000.00 |  |  | 200,000.00 |  |  | 100,000.00 |  |  |
| Library | 0 |  |  | 0 |  |  | 1 |  |  |  |  |  |  |  |  | 100,000.00 |  |  |
| Computer Lab. | 0 |  |  | 0 |  |  | 1 |  |  |  |  |  |  |  |  | 100,000.00 |  |  |
| a.3.3. School perimeter fence completed |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 80% |  |  | 90% |  |  | 100% |  |  | 50, 000.00 |  |  | 50, 000.00 |  |  | 50,000.00 |  |  |
| B. Quality and Relevance of Basic Education |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| b.1. Improved reading skills in English subjects |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| b.1.1. All students read within their standard reading level (independent readers) | 251 |  |  | 312 |  |  | 356 |  |  |  |  |  |  |  |  |  |  |  |
| b.2. Improved skills of pupils IN SCIENCE, MATHEMATICS, HEKASI, |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| b.2.1. Organized review classes in all subjects and grade levels starting from November 2010 to February 2018 and the years. | 13 classes |  |  | 13 classes |  |  | 13 classes |  |  |  |  |  |  |  |  |  |  |  |
| b.3. Improved Curriculum Implementation and Instructional Delivery |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| b.3.1. 100% of school days met or delivered per year | 100% |  |  | 100% |  |  | 100% |  |  |  |  |  |  |  |  |  |  |  |
| b.3.2. 100% of pupils are promoted considering the "no read, no move" principle of the Every Child a Reader Program (ECARP) | 100% |  |  | 100% |  |  | 100% |  |  |  |  |  |  |  |  |  |  |  |
| b.3.3. 100% of the Grade I entrants have ECD experiences | 100% |  |  | 100% |  |  | 100% |  |  |  |  |  |  |  |  |  |  |  |
| b.3.4. 100% of the Grade I Entrants have been positively considered under School Readiness Assessment | 100% |  |  | 100% |  |  | 100% |  |  |  |  |  |  |  |  |  |  |  |
| b.4. Improved subject knowledge/ teaching skills of teachers |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| b.4.1. Teachers were trained on results of NCBTS/TSNA | 6 |  |  | 6 |  |  | 4 |  |  | 120,000.00 |  |  | 120,000.00 |  |  | 80,000.00 |  |  |
| b.4.2. Teachers trained on computer literacy | 2 |  |  | 2 |  |  | 2 |  |  | 50,000.00 |  |  | 50,000.00 |  |  | 50,000.00 |  |  |
| b.4.3. 14 out of 14 teachers subscribed to professional magazines | 5 |  |  | 9 |  |  | 14 |  |  |  |  |  |  |  |  |  |  |  |
| b.4.4. 15 out of 15 teachers are master’s degree holder | 14 |  |  | 14 |  |  | 14 |  |  | 30,00 0.00 |  |  | 30,00 0.00 |  |  | 30,00 0.00 |  |  |
| b.4.5. 14 out of 14 teachers and Principal conducted one action research each a year | 15 |  |  | 15 |  |  | 15 |  |  |  |  |  |  |  |  |  |  |  |
| b.5. Improved Nutritional status of pupils |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| b.5.1. 100% of students within normal status of nutrition | 475 |  |  | 550 |  |  | 563 |  |  | 14,250.00 |  |  | 16,500.00 |  |  | 16,890.00 |  |  |
| b.5.2. Feeding | 6 months |  |  | 6 months |  |  | 6 months |  |  | 85,500.00 |  |  | 99,000.00 |  |  | 101,340.00 |  |  |
| Program implemented in 6 sustained months |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| C. School Management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| c.1. Instructional Supervision Strengthened |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| c.1.1. Frequency of supervision |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| School Head | 14 out of 14 monthly |  |  | 14 out of 14 monthly |  |  | 14 out of 14 monthly |  |  |  |  |  |  |  |  |  |  |  |
| PSDS | 14 out of 14 quarterly |  |  | 14 out of 14 quarterly |  |  | 14 out of 14 quarterly |  |  |  |  |  |  |  |  |  |  |  |
| ES | 14 out of 14/semester |  |  | 14 out of 14/semester |  |  | 14 out of 14/semester |  |  |  |  |  |  |  |  |  |  |  |
| c.1.2. Number of teacher supervised |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| School Head | 14 out of 14 monthly |  |  | 14 out of 14 monthly |  |  | 14 out of 14 monthly |  |  |  |  |  |  |  |  |  |  |  |
| PSDS | 14 out of 14/quarter |  |  | 14 out of 14/quarter |  |  | 14 out of 14 /quarter |  |  |  |  |  |  |  |  |  |  |  |
| ES | 14 of 14/semester |  |  | 14 of 14/semester |  |  | 14 of 14 /semester |  |  |  |  |  |  |  |  |  |  |  |
| c.2. Effective School Management and Administration Implemented |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| c.2.1 100% of teachers report to school on time. | 100% |  |  | 100% |  |  | 100% |  |  |  |  |  |  |  |  |  |  |  |
| c.2.2. 100% of teachers have no more than 1 day absence in a month. | 100% |  |  | 100% |  |  | 100% |  |  |  |  |  |  |  |  |  |  |  |
| c.2.3. 100% of the number of contact time observed by 2013 | 100% |  |  | 100% |  |  | 100% |  |  |  |  |  |  |  |  |  |  |  |
| c.2.4. 14 out of 14 teachers making home | 7 |  |  | 12 |  |  | 15 |  |  |  |  |  |  |  |  |  |  |  |
| visits |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| c.2.5. PTA board conducts 10 meetings in a school year | 10 |  |  | 10 |  |  | 10 |  |  | 10,000.00 |  |  | 10,000.00 |  |  | 10,000.00 |  |  |
| c.2.6. One School Governing Council organized and | 1 |  |  | 0 |  |  | 0 |  |  | 1,000.00 |  |  |  |  |  |  |  |  |
| c.2.7. Eight school INSET prepared and implemented. | 8 |  |  | 8 |  |  | 8 |  |  | 40,000.00 |  |  | 40,000.00 |  |  | 40,000.00 |  |  |
| c.3.1. Parents attendance to PTA activities. Number of parents attended PTA meetings |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Meeting | 300 |  |  | 330 |  |  | 360 |  |  |  |  |  |  |  |  |  |  |  |
| Brigada Eskwela | 340 |  |  | 350 |  |  | 360 |  |  |  |  |  |  |  |  |  |  |  |
| General PTCA Assembly | 300 |  |  | 330 |  |  | 360 |  |  |  |  |  |  |  |  |  |  |  |
| Homeroom PTCA | 300 |  |  | 330 |  |  | 360 |  |  |  |  |  |  |  |  |  |  |  |
| c.3.2. One (1) Alumni Association organized and made functional by 2011 | 1 |  |  | 0 |  |  | 0 |  |  | 5,000.00 |  |  |  |  |  |  |  |  |
| c.3.3. Increased Financial investment by LGU’s. Amount invested by LGU’s |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Source of funds |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Barangay (Brgy) | 1% of Brgy. EdCom |  |  | 1% of Brgy. EdCom |  |  | 1% of Brgy. EdCom |  |  |  |  |  |  |  |  |  |  |  |
| Brgy. SK | 1% of SK fund |  |  | 1% of SK fund |  |  | 1% of SK fund |  |  |  |  |  |  |  |  |  |  |  |
| SEF | 100,000 |  |  | 150,000 |  |  | 200,000 |  |  |  |  |  |  |  |  |  |  |  |
| c.3.4. Increased financial investment by PTCA. Amount invested by PTCA. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| GPTCA | P20, 000 |  |  | P25, 000 |  |  | P25, 000 |  |  |  |  |  |  |  |  |  |  |  |
| c.3.5. 100% of pupils are covered by the QUEEN program. | 60% |  |  | 80% |  |  | 100% |  |  |  |  |  |  |  |  |  |  |  |
| c.3.6. Percent of parents participation in Brigada Eskwela from 90% to 100% by 2013. | 100% |  |  | 100% |  |  | 100% |  |  |  |  |  |  |  |  |  |  |  |
| c.3.7. Four (4) private individuals and/or organizations/ corporations donate to the school in a school year. | 4 |  |  | 4 |  |  | 4 |  |  |  |  |  |  |  |  |  |  |  |
| c.4. Resource mobilization efforts intensified |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| c.4.1. Resource mobilization efforts conducted | P50, 000 |  |  | P50, 000 |  |  | P50, 000 |  |  |  |  |  |  |  |  |  |  |  |
| Name of resource mobilization program | P50, 000 |  |  | P50, 000 |  |  | P50, 000 |  |  |  |  |  |  |  |  |  |  |  |
| Mutya at Lakan ‘09 | P50, 000 |  |  | P50, 000 |  |  | P50, 000 |  |  |  |  |  |  |  |  |  |  |  |
| Christmas raffle |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| King and Queen of Hearts |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| c.5. Improved School Environment |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| c.5.1. Number of conflicts reduced |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Conflict |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Pupil– pupil conflict | 0 |  |  | 0 |  |  | 0 |  |  |  |  |  |  |  |  |  |  |  |
| Teacher – pupil conflict | 0 |  |  | 0 |  |  | 0 |  |  |  |  |  |  |  |  |  |  |  |
| Teacher – teacher conflict | 0 |  |  | 0 |  |  | 0 |  |  |  |  |  |  |  |  |  |  |  |
| Teacher – parent conflict | 0 |  |  | 0 |  |  | 0 |  |  |  |  |  |  |  |  |  |  |  |
| D. School |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Performance Indicators |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| d.1. Improved School Performance Indicators |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| d.1.1. Decreased simple dropout rate from 2.74% to 1% by 2013. | 2% |  |  | 1.50% |  |  | 1% |  |  |  |  |  |  |  |  |  |  |  |
| d.1.2. Decreased failure rate from 8 to1 % by 2013. | 5% |  |  | 3% |  |  | 1% |  |  |  |  |  |  |  |  |  |  |  |
| d.1.3. Maintained graduation rate of 100% until 2013. | 100% |  |  | 100% |  |  | 100% |  |  |  |  |  |  |  |  |  |  |  |
| d.1.4. Decreased repetition rate from 8.17% to 1% by 2013. | 5.50% |  |  | 3% |  |  | 1% |  |  |  |  |  |  |  |  |  |  |  |

ANNEXES

Indicate the Annexes attached.

Please attach the following:

- SRC/SIS

- Data Interpretation Template

- Streams Diagnostic Chart - Streams Objectives Chart

- Forecasted Data

- Site Development Plan